## Contract Log
Project Name | Address | Estimated Start Date | Estimated Completion Date | Vendor | PO# | Contract Status | Vendor | PO# | Contract Status | Vendor | PO# | Contract Status | Vendor | PO# | Contract Status | Vendor | PO# | Contract Status
HRP Holbrook | Asheville, NC | 2024-10-01 |  | Zavala | 2411 $243,965 | Fully Executed | Pristine |  | Fully Executed
Pines at Peach | Raleigh, NC | 2024-07-01 |  | Pristine | 2216 $337,788 | Fully Executed | Zavala-NO PO |  |  | Bruzz-NO PO |  | Fully Executed
Gatebay (Inv 2080/2081/2103) | Henderson, NC | 2024-10-01 | 2024-11-01 | Pristine | 2378 $38,896 | Fully Executed
Mountain Glen | Brevard, NC | 2024-09-01 |  | Zavala | 2366 $56,964.02 | Fully Executed | Pristine | 2496 $88,825.00 | Fully Executed | Martinez-NO PO |  |  | Towa-NO PO |  |  | JGBR - Has PO's but not sure how to get this to them now? |  |  | Missing info to draft contract
Aaron Mills | Martinsville, VA | 2025-05-25 |  |  |  |  | Pristine-Per OC PO not ready 8/12/25 | Chris 4/28
DHIC: Sedgebrook | Cary, NC | 2025-01-01 |  | Zavala | 2526 | Fully Executed | JSH Windows/Siding | 2862/2863 | Fully Executed | Anzola Trim-NO PO
DHIC: Jeffries Ridge (Alli) | Raleigh, NC | 2024-12-01 |  | Zavala | 2523 | Fully Executed | Pristine | 2842 $201,646.00 | Fully Executed | CIE (interior) | 2557 $26,226.00 *PO had note 'need to be edited' - emailed OC 6/25 |  | Towa | no PO in QB |  |  |  |  | Created - Awaiting Signatures
DHIC: Ripley Station (Starting interior & siding July 2025) | Raleigh, NC |  |  | Zavala | 2525 | Fully Executed | Rubio & Pristine | 3170, 3243, 3246-Rubio; 3244, 3245 Pristine | Rubio 3170 Fully Executed; Pristine 3244 Fully Executed; Rubio 3243 Fully Executed; Pristine 3403 Fully Executed; Rubio 3246 Fully Executed; Pristine 3245 created by SA and awaiting signatures | Anzola Trim (Joe) wait for PO |  |  | Towa-NO PO |  |  | Amber | NO PO# | Created - Awaiting Signatures | Sub Executed - Need Wesco Signatures
DHIC: Madison Glen | Raleigh, NC |  |  | Zavala | 2524 & 3883 | Fully Executed | Pristine (Siding & WIndows) | 3884 | Created - Awaiting Signatures | Anzola Trim (Joe) wait for PO |  |  | Towa-NO PO | [5 empty] | Fully Executed
DHIC: Avonlea Apartments | Raleigh, NC | 2025-01-01 |  | Zavala | 2521 | Fully Executed | Rubio Siding/Windows | 2960 $286,564.00 3062 $24,045.00 | Fully Executed | Anzola Trim (Joe) wait for PO |  |  | Towa-NO PO |  |  | JSH - NO PO |  |  | To Be Completed
DHIC: Tryon Grove | Raleigh, NC |  |  | Zavala-8/12 OC checking PO - 9/24/25 Updated to Rooster Roofing RK | Rooster Roofing 3322 | Fully Executed | JSH Windows/Siding Gave to Joe 8/7/25 & 9/3/25 | 3164, 3188, 3167, 3190 | Created - Awaiting Signatures | Pristine | 3163-Bldg 2500 only | Fully Executed | Towa-NO PO |  |  | JSH chase
DHIC: Highland Village | Cary, NC |  |  | Zavala | 2522 | Fully Executed | TBD Siding |  |  | CIE (interior) or Anzola |  |  | Towa-NO PO
Bond Deal 3: Ridgeway (not started - Aug/Sept 2025 start) | Taylorsville, NC |  |  | Zavala | 2443 (Oscar to follow up 6/18) | Created - Awaiting Signatures |  |  |  | Bruzz? |  |  | Towa-NO PO
Bond Deal 3: Brookside | Maxton, NC |  |  | Pristine | 2720? Note: SA need OC help |  | Anzola/Martinez |  |  | Guillermo Shutters
Bond Deal 3: Berry Park | Chadbourn, NC | [5 empty] | Bruzz Interior |  |  | Guillermo Shutters |  |  | Towa-NO PO
Bond Deal 3: Chadwick Place | Chadbourn, NC | [5 empty] | Bruzz Interior |  |  | Guillermo Shutters - not set up
Bond Deal 3: Piney Pointe | Hamlet, NC | [5 empty] | Martinez | [5 empty] | Towa-NO PO
Bond Deal 3: Brittany Place | Washington, NC | [5 empty] | Martinez |  |  | Bruzz
Bond Deal 3: British Woods ************ This is where we start again 6/26**** | Roanoke Rapids, NC
Bond Deal 3: Burnside Village | Hookertown, NC | [5 empty] | Martinez |  |  | Bruzz? |  |  | Towa-NO PO
Bond Deal 3: Gooden Village | Elizabethcity, NC | [8 empty] | Anzola Trim (Joe) |  |  | Towa-NO PO
Bond Deal 3: Pine Ridge | Avery, NC
Bond Deal 3: Ridgeview | Sparta, NC
Bond Deal 3: Ridgeway | Taylorsville, NC |  |  | Amber Construction | 3948 (OLD) | Created - Awaiting Signatures | Bruzz-gave to CO 5/15 | 4044 | Created - Awaiting Signatures | Amber emailed 5/15 | 4045 | Fully Executed
Bond Deal 3: River Park | Sylva, NC
Bond Deal 3: Scotland Arms | Scotland Neck, NC
Bond Deal 3: Woodfield | Fairmont, NC
Partnership: Park Place Apartments | Snow Hill, NC
Partnership: Crest Knolls | Taylorsville, NC
Partnership: Gatebay Apartments | Conway, NC
Partnership: Regal Oaks | Hendersonville, NC
Partnership: Greenfield Manor | Mullins, SC |  |  | Amber Construction | 3903 | Fully Executed
Brian Dloniak | GSO, NC |  |  | Zavala | NO PO# | Fully Executed
Partnership: British Woods | Roanoke Rapids, NC |  |  | Zavala-emailed 5/15 | 4051 | Fully Executed
Partnership: Colony Woods | Roanoke Rapids, NC |  |  | Zavala-emailed 5/15 | 4050 | Fully Executed
Partnership: Long Branch | Dillon, SC |  |  | Bruzz | PO# 4033 | Fully Executed | Amber emailed 5/15 | 4048 | Fully Executed
Partnership: Mill Pond | Dillon, SC |  |  | Bruzz | 4025 | Fully Executed | Amber | 4024 | Fully Executed
Partnership: Silver Trace | Marion, SC |  |  | Amber Construction | NO PO# | Fully Executed
Partnership: River Bend | Fair Bluff, NC |  |  | Amber Construction | PO# 4086-6/4 emailed to Amber | Fully Executed
Partnership: Berry Court | Chadbourn, NC |  |  | Amber Construction 6/5 | PO# 4091 6/5 emailed to Amber | Fully Executed | Bruzz 6/5 Printed gave to CO | 4090 | Created - Awaiting Signatures | Pristine 6/5 Printed gave to CO | 4092 | Created - Awaiting Signatures
Partnership: Lake View | Lake View, SC |  |  | Bruzz | 4017 | Fully Executed | Amber emailed 5/15 | 4054 | Fully Executed
Partnership: Palmetto | Darlington, SC |  |  | Bruzz | NO SHOW |  | Amber emailed w/ SOW 6/16 |  | Fully Executed
KMW: James A Walker | Wilmington, NC |  |  | Rogelio - 7/14 put on front desk | No PO | Created - Awaiting Signatures
Anzola BD3 Fully Executed
Anzola DHIC Fully Executed

## Estimate and Scheduling Req
Customer | 1st Contact | Property | Location | Scope
Partnership - Jennifer Hatcher | 2025-04-03 | Greenfield Manor | Mullins, SC | PM: Can you price the windows for this building 193. Building 191 and 195 are brick with wooden gables. I’d like to finish that street off and move around to 1101 is all wooden and 1103 is brick with wooden gables. RESPONSE:I do have a question. Only Windows for Building 193, siding is complete. Are the rest of the buildings on the street side 191,195,1101,11,03,1105,1107 needing the windows as well as we do siding? Are we doing 1105 & 1107? PM: Yes, siding and windows for those units.
Partnership - Kellie Atkins | 2025-04-30 | Mallard Creek | Auroura, NC 27806 | Replace 22 exterior storage doors - 36 X 80 (Photo to right)
Partnership - Kellie Atkins | Estimate Provided-waiting on approval | Park Place | Snow Hill, NC | $26K Quote
Partnership - Kellie Atkins | 2025-04-28 | Park Place | Snow Hill, NC | We also have an existing gazebo there that the floor needs to be replaced however I would like to get a quote to fill in the hole under it with concrete and just build a new shelter. If I could get quotes separately that would be great .
Partnership - Nadia Gallovich | Work approved 5/2/25 - Need dates for contract $110,250 | Wilmington Court | Wallace, NC | 160 window replacements
Partnership - Nadia Gallovich | 2025-05-21 | Oak Ridge | Wallace, NC | 16 breezeway windows replaced
Partnership - Tracy Young | Estimate Provided-waiting on approval | Palmetto |  | Siding & Windows - 7/8/25 added shutter request
Partnership - Jennifer Hatcher |  | Gatebay | Conway, SC | Gate Bay over bldg. 11 and 12 in Conway. (photo to right)
Partnership |  | Pinetree Apartments? | Oxford, NC

## Vehicle Log-1st Meeting
Year | Model/Make | Driver | Plate # | Title last 5 digits | Vin # | Renewal Date | Paid Date | Interest Rate | Notes:
2016 | Silverado C2500 | Service Truck | JK8642 | 65372 | 1GB1CUE82GF269081 | 2024-12-31 | 2025-01-07
2019 | Chevy 3500 Dually | Wes Atkinson | JR1324 | 29941 | 1GC4KXEY9KF129941 | 2025-01-31 | 2024-12-01
2024 | Toyota Tundra | Chris OKeefe | LAL9805 | 85175 | 5TFKB5DB3RX185175 | 2025-07-31 |  | 8.79% | Need 2nd key fob from dealer
2024 | Toyota Rav 4 | Oscar Centeno | LAM1425 | 77918 | 2T3H1RFVXRC277918 | 2025-07-31 | 2025-05-27 | 4.49%
2017 | Chevy Suburban | Wes Atkinson | FFJ8206 | 33947 | 1GNSKJKC2HR284780 | 2025-06-30
2020 | Chevy Silverado 2500 | Jesse Warren | KB9444 | 97947 | 1GC1YLEY3LF245650 | 2025-07-31 | 2025-07-25
2024 | Toyota Tundra | Joe St. John | LEJ5502 | 26165 | 5TFLA5DBXRX228031 | 2025-12-31 | 2024-12-01 | 4.99%
2017 | Chevy Truck | Chuck Atkinson | EHB4862 | 40947 | 1GCVKREC6HZ169664 | 2025-01-31 |  |  | 2/2025 Wrecked
2017 | Cadillac Escalade | Evie Atkinson |  |  | 1GYS4HKJ9HR385416
Year | Model/Make | Driver | Last Oil Change Date/Mileage | Other Service/Date
2016 | Silverado C2500 | Service Truck
2019 | Chevy 3500 Dually | Wes Atkinson
2017 | Chevy Suburban | Wes Atkinson
2024 | Toyota Tundra | Chris OKeefe
2024 | Toyota Rav 4 | Oscar Centeno
2020 | Chevy Silverado 2500 | Jesse Warren
2024 | Toyota Tundra | Joe St. John
2017 | Chevy Truck | Chuck Atkinson
2017 | Cadillac Escalade | Evie Atkinson

## 6.4.26
2025 Wesco Notebook |  | Topics | Team Meeting 6.3.26 Present: Wes, Stephanie, Oscar, Joe, Chris, Rebecca
|  | 1.) | Do we need any contracts for subcontractors? Turn in subcontractor recipts, Review Towa, Martinez, Bruzz
|  | 2.) | Scope
|  | 3.) | Contract Request
4.)
5.)
| PROJECT SUMMARY | [14 empty] | Be sure to include the job name, building number, and/or unit number on the invoice.
| Project Name | Customer/ Owner | Start Date | Estimated Job Completion Date | SharePoint Link | Proj Mgr | Scope | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | PM Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Others Action Items | Customer Contracts Executed | EXECUTED SUBCONTRACTS
| BD3 Ridgeway | KMW | TBD | TBD |  | Chris | build lean to |  |  |  | Build mailbox addition on maintenance shed. Spoke with Heitor waiting on architect/owners to decide DRAFT CO# 1786 $0.99 | Follow- up | RK contract
| Concord | KMW | 2026-06-01 | 2027-01-01 | Link | Chris 8989 | Interior/Exterior |  |  |  | EST 1568 - in Oscar's court - sections have been sent to him
| DHIC Avonlea HILLSTONE WORK | KMW | 2025-03-01 | 2026-06-18 |  | Joe |  |  |  |  | Wesco retention billed 6/5 - Hillstone contract was closed, but reopened so they could bill for rails at dumpster area due to sidewalk slope, Window sash to be replaced 5017 2unit 201 by Pristine 6-18
| DHIC Highland | KMW | 2025-12-01 | 2026-06-30 |  | Joe |  |  |  |  | Fence on top of block wall Window opening control device on windows! | PO 3480 - HC Door Order - swing per plans
| DHIC Madison Glen | KMW | 2026-02-01 | 2026-07-17 |  | Joe |  |  |  |  | Pristine-Siding the office, 6800, and 6820. Rigo to finish framing 6-19-26. Punch work completed on 7 buildings, will need to add new blinds at 6820 after windows get replaced |  | Ord 4.14.26 Trucks 6, 7 est del by 5/7 , waiting on ETA for 10, 11 Ordered SA - We have no profit here...review pay app
| DHIC Ripley | KMW | 2025-10-01 | 2026-07-30 |  | Joe |  |  |  |  | Stairs are raised for epoxy and need to get rails replaced
| DHIC Sedgebrook* | KMW | 2025-05-01 | 2026-06-30 |  | Joe |  |  |  |  | Need to get dumpster fences installed-cleared after 6-18-26
| DHIC Tryon | KMW | 2025-07-01 | 2026-04-30 |  | Joe |  |  |  |  | Additional areas were worked with epoxy, will require Pristine to return next week to remove siding and install flashing and siding again. CO 1793 In Procore passed inspections 5/7/26 and will complete this work the week of 5/11 CO 1795 In Procore -6 thresholds and door shoes for riser rooms after doors were cut down for concrete In Procore Door shoes have been installed, will install thresholds this week when we return for siding installation.
| River Bend | Partnership
| Green Valley | HRP |  |  | Link | Chris 8989 | Siding | [5 empty] | Are we invoicing for elevator pits or will that be in the contract?
| Greenfield | Partnership | 2026-04-06 |  | Link | Chris | Siding / Windows | [6 empty] | YES | YES Amber
| Holbrook | HRP | 2024-10-01 | 2026-06-01 | Home | Chris | Siding/Roof/Gutter | Pristine M-F | Pristine M-F |  | Need to get a very accurate inventory of what's on the ground and in trailers. Would like to consolidate. | CO 1772 Draft | RK - Any retention updates for upcoming 5/15 billing - next building? | YES | YES Zavala & YES Pristine
| Lakeview | Partnership | 2026-04-27 | /15/26 | Link | Chris | Exterior | [6 empty] | YES
| Long Branch | Partnership |  |  | Link | Chris | Exterior | [6 empty] | YES
| Martins Landing | Partnership | 2026-03-10 |  | Link | Chris | Roof | [6 empty] | YES | NO
| Maynard - APS | KMW | 2025-07-01 |  | Link | Wes | Siding
| Meadowview | KMW | 2025-09-01 |  | Link | Chris | Exterior & Interior |  |  |  | We are giving an estimate for Siding for this job as well
| Mill Pond | Partnership | 2026-04-27 | 2026-05-15 | Link | Chris | Exterior | [6 empty] | YES
| Palmetto | Partnership | 2026-03-16 |  | Link | Chris | Siding / Windows
| River Park | KMW |  |  |  | Chris
| Scotland | KMW |  |  |  | Joe
| Silver Trace | Partnership |  |  | Silver Trace WescoSOW & Estimate.xlsx | [5 empty] | We have a contract for this, but no start dates and it is not on the team meeting notes |  |  | Need dates
Greenfield Manor
Silver Trace
| Berry Court | Partnership | 2026-06-08 | 2026-06-12 | [6 empty] | we will need to go back to finish this
| Upcoming Projects | Customer/ Owner | EstimatedStart Date | Estimated Job Completion Date | SharePoint Link | Proj Mgr | Scope | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded
| Palmetto | Partnership |  |  |  |  | Siding / Windows
| Pipeline/Bids | Customer/ Owner | Estimated Start Date | Estimated Job Completion Date | SharePoint Link | Proj Mgr | Scope
| Mock Place | KMW | TBD |  |  |  | Reno
| James A Walker | KMW | TBD |  |  |  | Interior Reno & some Exterior
| Gatebay II | Partnership | TBD |  |  |  | Siding
| Green Valley | HRP | TBD |  |  |  | Siding
| Clemmons Village | HRP | TBD |  |  |  | Siding
| The Grayson | KMW | TBD |  |  |  | Siding / Gutters
| Pinetree | Partnership | TBD |  |  |  | Windows
| Oak Ridge | Partnership | TBD |  |  |  | Windows
| West Forest | Partnership | TBD |  |  |  | Windows
| Hixson | HRP | TBD |  |  |  | Siding
| Tanyard Branch | KMW | TBD |  |  |  | Siding
| Sealand Valley | KMW | TBD |  |  |  | Siding
| Wilmington Court | Partnership | TBD |  |  |  | Windows |  |  |  | will be adding another estimate for doors, picnic shelter
| Granville Place/Plaza | KMW | TBD |  |  |  | Reno

## To Do
Task Summary
Project Name | Proj Mgr | PM Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Others Action Items
BD3 Ridgeway | Chris | Follow- up | RK contract
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
Concord | Chris 8989 | 0 | 0
DHIC Avonlea HILLSTONE WORK | Joe | 0 | 0
DHIC Highland | Joe | PO 3480 - HC Door Order - swing per plans | 0
DHIC Madison Glen | Joe | 0 | Ord 4.14.26 Trucks 6, 7 est del by 5/7 , waiting on ETA for 10, 11 Ordered SA - We have no profit here...review pay app
DHIC Ripley | Joe | 0 | 0
DHIC Sedgebrook* | Joe | 0 | 0
DHIC Tryon | Joe | 0 | 0
0 | 0 | 0 | 0
River Bend | 0 | 0 | 0
Green Valley | Chris 8989 | 0 | Are we invoicing for elevator pits or will that be in the contract?
Greenfield | Chris | 0 | 0
Holbrook | Chris | CO 1772 Draft | RK - Any retention updates for upcoming 5/15 billing - next building?
Lakeview | Chris | 0 | 0
Long Branch | Chris | 0 | 0
Martins Landing | Chris | 0 | 0
Maynard - APS | Wes | 0 | 0
Meadowview | Chris | 0 | 0
Mill Pond | Chris | 0 | 0
Palmetto | Chris | 0 | 0
River Park | Chris | 0 | 0
Scotland | Joe | 0 | 0
Silver Trace | 0 | 0 | 0
Greenfield Manor | 0 | 0 | 0
Silver Trace | 0 | 0 | 0
0 | 0 | 0 | 0
Upcoming Projects | Proj Mgr | 0 | 0
Palmetto | 0 | 0 | 0
0 |  |  | 0
0 |  |  | 0
0 |  |  | 0
0

## 6.26.25
Team Meeting
6.26.25
Present: Wes, Oscar, Joe, Carson & Stephanie & Rebecca (Septet Team, PRESENT)
Topics
1.) | Colonial Life @ 12
2.) | Contract Log
3.) | Estimate/Scheduling
4.) | Invoice review - Inventory
5.) | Oil changes and tires
6.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
7.) | Pay Apps
8.)
9.)
PROJECTS | [8 empty] | Be sure to include the job name, building number, and/or unit number on the invoice.
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | x | Pristine |  |  | Punch lists for Building 7 & 8 are ready, still waiting on the list from HRP to close out 5 & 6. When we have Siks guys back out there they need to seal the gutter that is leaking on 5. Chris will schedule them for later this week. We also need to get some siding to replace the wall they have been pulling off of in Building 10. | Need to get the siding to replenish the wall they have been pulling off of, also get them scheduled to start the punch work. | 2024-08-01 | Done
Pines @ Peach | Joe | Pristine |  |  | Outside of 3 done / Working on Outside of 2 - KMW has Pissed off the owners. Change order for Ceilings at top floors & Breezeways has been approved. 2 crews are working on re-insulating the windows on backside on buildings 3 and 2 Also have the same crews working on the breezeways Along with putting in flashing and 2x10 in place (flashing taped and flex taped all joints along with ty-vec work) (Porches are back flush on buildings 2 & 3) | CHANGE ORDERS??? |  | Done
Mountain Glen | x | Pristine / Rigo |  |  | Rigo was installing doors in the UFAS units, sample walls for siding have been hung on building 144 for viewing. Siding order will ship 12/3 and will arrive 12/5 - 12/6. Last truck of doors was delivered by Sik Sunday 12/1. Consolidate containers on site so that we have room to store our siding, and need to be prepared to unload siding when it arrives. | Need to find out what JGBR will be doing at Mountain Glen with Phillip, weather it is exterior work or interior work. Confirm if exterior doors are in the trailer Sik hauled up Sunday.
Holbrook | x | Pristine / Zavala |  |  | Zavala has his guys starting to felt Building 3 (Type 3). They have shingles on all amenities and garages. Building 2 also has shingles on it and now needs only the metal roofing. Jonathan also has sent us the material list for the metal he will be needing. | Call Jonathan, and make sure he has guys on site to unload truck of siding. (Carefully)
Dloniak House | Crawl Diddy | Pinnacle |  |  | Huntley - Bricking Chimney & House , PEM (plumbing)- waiting on tubs / (electrical) - lighting in kitchen and porches / (HVAC) - relocating lines & gas lines, Steve (Pro Chem) - after PME finished | Inspections? Getting tied into city- Hub cast iron? Gas Lines? Temp power? Structural Protection infront of plumbing fixtures in garages
Woodfield - BD3 | Joe |  |  |  | Should finish 3/7/25
Aaron Mills |  | Pristine
Jeffries -DHIC | Joe
Avonlea - DHIC | Joe
Sedgbrook - DHIC | Joe
Piney Pointe - BD3 | Joe
Brookside - BD3 | Joe
Burnside - BD3 | Joe
Brittany Place - BD3 | Joe
Scotland Arms - BD3 | Joe
British Arms - BD3 | Joe
River Park - BD3 |  |  | Rigo |  | Monday - 6-23-25 Rigo starting UFAS units 6 & 16 Demo & Framing
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Tryon- DHIC | Joe
Ripley - DHIC | Joe
Highland Village- DHIC | Joe
Madison Glen - DHIC | Joe
Pine Ridge- BD3
Pine View- BD3
Ridgeway- BD3
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22 * *Again 10-23-24*
KMW - Maynard Rd.

## 6.19.25
Team Meeting
6.19.25
Present: Wes, Oscar, Joe, Carson & Stephanie & Rebecca (Septet Team, PRESENT)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Contract Log
3.) | BCBS 7.1 Renewal
4.) | Invoice review - Inventory
5.) | Oil changes and tires
6.) | Change Order Review & New Process - need info/email to right
7.) | OneStep GPS Tracker
8.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
9.)
PROJECTS | [8 empty] | Be sure to include the job name, building number, and/or unit number on the invoice.
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch lists for Building 7 & 8 are ready, still waiting on the list from HRP to close out 5 & 6. When we have Siks guys back out there they need to seal the gutter that is leaking on 5. Chris will schedule them for later this week. We also need to get some siding to replace the wall they have been pulling off of in Building 10. | Need to get the siding to replenish the wall they have been pulling off of, also get them scheduled to start the punch work. | 2024-08-01 | Done
Pines @ Peach | Joe | Pristine |  |  | Outside of 3 done / Working on Outside of 2 - KMW has Pissed off the owners. Change order for Ceilings at top floors & Breezeways has been approved. 2 crews are working on re-insulating the windows on backside on buildings 3 and 2 Also have the same crews working on the breezeways Along with putting in flashing and 2x10 in place (flashing taped and flex taped all joints along with ty-vec work) (Porches are back flush on buildings 2 & 3) | CHANGE ORDERS??? |  | Done
Mountain Glen | Chris | Pristine / Rigo |  |  | Rigo was installing doors in the UFAS units, sample walls for siding have been hung on building 144 for viewing. Siding order will ship 12/3 and will arrive 12/5 - 12/6. Last truck of doors was delivered by Sik Sunday 12/1. Consolidate containers on site so that we have room to store our siding, and need to be prepared to unload siding when it arrives. | Need to find out what JGBR will be doing at Mountain Glen with Phillip, weather it is exterior work or interior work. Confirm if exterior doors are in the trailer Sik hauled up Sunday.
Holbrook | Chris | Pristine / Zavala |  |  | Zavala has his guys starting to felt Building 3 (Type 3). They have shingles on all amenities and garages. Building 2 also has shingles on it and now needs only the metal roofing. Jonathan also has sent us the material list for the metal he will be needing. | Call Jonathan, and make sure he has guys on site to unload truck of siding. (Carefully)
Dloniak House | Crawl Diddy | Pinnacle |  |  | Huntley - Bricking Chimney & House , PEM (plumbing)- waiting on tubs / (electrical) - lighting in kitchen and porches / (HVAC) - relocating lines & gas lines, Steve (Pro Chem) - after PME finished | Inspections? Getting tied into city- Hub cast iron? Gas Lines? Temp power? Structural Protection infront of plumbing fixtures in garages
Woodfield - BD3 | Joe |  |  |  | Should finish 3/7/25
Aaron Mills |  | Pristine
Jeffries -DHIC | Joe
Avonlea - DHIC | Joe
Sedgbrook - DHIC | Joe
Piney Pointe - BD3 | Joe
Brookside - BD3 | Joe
Burnside - BD3 | Joe
Brittany Place - BD3 | Joe
Scotland Arms - BD3 | Joe
British Arms - BD3 | Joe
River Park - BD3 |  |  | Rigo |  | Monday - 6-23-25 Rigo starting UFAS units 6 & 16 Demo & Framing
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Tryon- DHIC | Joe
Ripley - DHIC | Joe
Highland Village- DHIC | Joe
Madison Glen - DHIC | Joe
Pine Ridge- BD3
Pine View- BD3
Ridgeway- BD3
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22 * *Again 10-23-24*
KMW - Maynard Rd.

## 5.21.25
Team Meeting
5.21.25
Present: Wes, Oscar, Joe, Carson & Stephanie & Rebecca (Septet Team, PRESENT)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Contract Log
3.) | Yale front door codes?
4.) | Invoice review - Inventory
5.) | Dario - RK Emailed him 3x, SA texted him daily - still no paperwork - he is not authorized to be onsite yet
6.) | Change Order Review & New Process - need info/email to right
7.) | OneStep GPS Tracker
8.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
9.)
PROJECTS | [8 empty] | Be sure to include the job name, building number, and/or unit number on the invoice.
Current Projects (Start Date) | Project Manager (always Chris & Joe) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch lists for Building 7 & 8 are ready, still waiting on the list from HRP to close out 5 & 6. When we have Siks guys back out there they need to seal the gutter that is leaking on 5. Chris will schedule them for later this week. We also need to get some siding to replace the wall they have been pulling off of in Building 10. | Need to get the siding to replenish the wall they have been pulling off of, also get them scheduled to start the punch work. | 2024-08-01 | Done
Pines @ Peach | Joe | Pristine |  |  | Outside of 3 done / Working on Outside of 2 - KMW has Pissed off the owners. Change order for Ceilings at top floors & Breezeways has been approved. 2 crews are working on re-insulating the windows on backside on buildings 3 and 2 Also have the same crews working on the breezeways Along with putting in flashing and 2x10 in place (flashing taped and flex taped all joints along with ty-vec work) (Porches are back flush on buildings 2 & 3) | CHANGE ORDERS??? |  | Done
Mountain Glen | Chris | Pristine / Rigo |  |  | Rigo was installing doors in the UFAS units, sample walls for siding have been hung on building 144 for viewing. Siding order will ship 12/3 and will arrive 12/5 - 12/6. Last truck of doors was delivered by Sik Sunday 12/1. Consolidate containers on site so that we have room to store our siding, and need to be prepared to unload siding when it arrives. | Need to find out what JGBR will be doing at Mountain Glen with Phillip, weather it is exterior work or interior work. Confirm if exterior doors are in the trailer Sik hauled up Sunday.
Holbrook | Chris | Pristine / Zavala |  |  | Zavala has his guys starting to felt Building 3 (Type 3). They have shingles on all amenities and garages. Building 2 also has shingles on it and now needs only the metal roofing. Jonathan also has sent us the material list for the metal he will be needing. | Call Jonathan, and make sure he has guys on site to unload truck of siding. (Carefully)
Dloniak House | Crawl Diddy | Pinnacle |  |  | Huntley - Bricking Chimney & House , PEM (plumbing)- waiting on tubs / (electrical) - lighting in kitchen and porches / (HVAC) - relocating lines & gas lines, Steve (Pro Chem) - after PME finished | Inspections? Getting tied into city- Hub cast iron? Gas Lines? Temp power? Structural Protection infront of plumbing fixtures in garages
Woodfield - BD3 | Joe |  |  |  | Should finish 3/7/25
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Aaron Mills | Chris | Pristine |  | Brandon | Framing in Process
Jeffries -DHIC | Joe
Avonlea - DHIC | Joe
Sedgbrook - DHIC | Joe
Piney Pointe - BD3 | Joe
Brookside - BD3 | Joe
Woodfield - BD3 | Joe
Burnside - BD3 | Joe
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22 * *Again 10-23-24*
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 4.25.25
Team Meeting
4.25.25
Present: Wes, Oscar, Joe, Carson & Stephanie & Rebecca (Septet Team, PRESENT) - we need more space, more chairs - Chris on Phone, Sick Boi
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Contract Log
3.) | Alarm/Doors/Gates in 208 - does everyone know how to operate
4.) | Invoice review
5.) | Jesus, JSH Update
6.) | Change Order Review
7.) | Pay App Review - Bond Deal Little Jobs Done?
8.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
9.) | Make sure all completed jobs are billed
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch lists for Building 7 & 8 are ready, still waiting on the list from HRP to close out 5 & 6. When we have Siks guys back out there they need to seal the gutter that is leaking on 5. Chris will schedule them for later this week. We also need to get some siding to replace the wall they have been pulling off of in Building 10. | Need to get the siding to replenish the wall they have been pulling off of, also get them scheduled to start the punch work. | 2024-08-01 | Done
Pines @ Peach | Joe | Pristine |  |  | Outside of 3 done / Working on Outside of 2 - KMW has Pissed off the owners. Change order for Ceilings at top floors & Breezeways has been approved. 2 crews are working on re-insulating the windows on backside on buildings 3 and 2 Also have the same crews working on the breezeways Along with putting in flashing and 2x10 in place (flashing taped and flex taped all joints along with ty-vec work) (Porches are back flush on buildings 2 & 3) | CHANGE ORDERS??? |  | Done
Mountain Glen | Chris | Pristine / Rigo |  |  | Rigo was installing doors in the UFAS units, sample walls for siding have been hung on building 144 for viewing. Siding order will ship 12/3 and will arrive 12/5 - 12/6. Last truck of doors was delivered by Sik Sunday 12/1. Consolidate containers on site so that we have room to store our siding, and need to be prepared to unload siding when it arrives. | Need to find out what JGBR will be doing at Mountain Glen with Phillip, weather it is exterior work or interior work. Confirm if exterior doors are in the trailer Sik hauled up Sunday.
Holbrook | Chris | Pristine / Zavala |  |  | Zavala has his guys starting to felt Building 3 (Type 3). They have shingles on all amenities and garages. Building 2 also has shingles on it and now needs only the metal roofing. Jonathan also has sent us the material list for the metal he will be needing. | Call Jonathan, and make sure he has guys on site to unload truck of siding. (Carefully)
Dloniak House | Crawl Diddy | Pinnacle |  |  | Huntley - Bricking Chimney & House , PEM (plumbing)- waiting on tubs / (electrical) - lighting in kitchen and porches / (HVAC) - relocating lines & gas lines, Steve (Pro Chem) - after PME finished | Inspections? Getting tied into city- Hub cast iron? Gas Lines? Temp power? Structural Protection infront of plumbing fixtures in garages
Woodfield - BD3 | Joe |  |  |  | Should finish 3/7/25
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Aaron Mills | Chris | Pristine |  | Brandon | Framing in Process
Jeffries -DHIC | Joe
Avonlea - DHIC | Joe
Sedgbrook - DHIC | Joe
Piney Pointe - BD3 | Joe
Brookside - BD3 | Joe
Woodfield - BD3 | Joe
Burnside - BD3 | Joe
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22 * *Again 10-23-24*
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 3-12.25
Team Meeting
3.12.25
Present: Wes, Oscar, Chris, Joe, Carson & Stephanie & Rebecca (Septet Team, PRESENT) - we need more space, more chairs
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Calendar - use to help track Change Order Work
3.) | Signed, CLOSING on Building for down the street
4.)
5.)
6.)
7.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
8.) | Make sure all completed jobs are billed
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch lists for Building 7 & 8 are ready, still waiting on the list from HRP to close out 5 & 6. When we have Siks guys back out there they need to seal the gutter that is leaking on 5. Chris will schedule them for later this week. We also need to get some siding to replace the wall they have been pulling off of in Building 10. | Need to get the siding to replenish the wall they have been pulling off of, also get them scheduled to start the punch work. | 2024-08-01 | Done
Pines @ Peach | Joe | Pristine |  |  | Outside of 3 done / Working on Outside of 2 - KMW has Pissed off the owners. Change order for Ceilings at top floors & Breezeways has been approved. 2 crews are working on re-insulating the windows on backside on buildings 3 and 2 Also have the same crews working on the breezeways Along with putting in flashing and 2x10 in place (flashing taped and flex taped all joints along with ty-vec work) (Porches are back flush on buildings 2 & 3) | CHANGE ORDERS??? |  | Done
Mountain Glen | Chris | Pristine / Rigo |  |  | Rigo was installing doors in the UFAS units, sample walls for siding have been hung on building 144 for viewing. Siding order will ship 12/3 and will arrive 12/5 - 12/6. Last truck of doors was delivered by Sik Sunday 12/1. Consolidate containers on site so that we have room to store our siding, and need to be prepared to unload siding when it arrives. | Need to find out what JGBR will be doing at Mountain Glen with Phillip, weather it is exterior work or interior work. Confirm if exterior doors are in the trailer Sik hauled up Sunday.
Holbrook | Chris | Pristine / Zavala |  |  | Zavala has his guys starting to felt Building 3 (Type 3). They have shingles on all amenities and garages. Building 2 also has shingles on it and now needs only the metal roofing. Jonathan also has sent us the material list for the metal he will be needing. | Call Jonathan, and make sure he has guys on site to unload truck of siding. (Carefully)
Dloniak House | Crawl Diddy | Pinnacle |  |  | 3rd party Footing Inspection for Pinnacle Footers due to bad weather and emailed a copy of the Inspection to City of Greensboro (James Wolffe) / (Huntley Brothers) are wrapping up foundation perimeter (CMU block, brick and mortar) *Trash Dumpster is on site along with porty potty* CONTACTED Castro (framer) & Riverside Truss - Cliff (trusses) they want to meet 12/24 at 9AM and call Steve (Pro-Chem) for Termite spray before fondation inspection | HOA Approval for Shingle and Metal color / Cables at front of site need to be burried lower for driveway (Call contacts on email)
Woodfield - BD3 | Joe |  |  |  | Should finish 3/7/25
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Aaron Mills | Chris | ? |  |  | Framing in Process
Jeffries -DHIC | Joe
Avonlea - DHIC | Joe
Sedgbrook - DHIC | Joe
Piney Pointe - BD3 | Joe
Brookside - BD3 | Joe
Woodfield - BD3 | Joe
Burnside - BD3 | Joe
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22 * *Again 10-23-24*
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 3-26.25
Team Meeting
2025-03-26
Present: Wes, Oscar, Joe, Carson & Stephanie & Rebecca (Septet Team, PRESENT) - we need more space, more chairs
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Calendar - use to help track Change Order Work
3.) | Flooring - 3/28, 2 offices and conference room in back
4.) | 208 Door codes
5.) | Invoices -
6.) | Vendor set -up
7.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
8.) | Make sure all completed jobs are billed
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch lists for Building 7 & 8 are ready, still waiting on the list from HRP to close out 5 & 6. When we have Siks guys back out there they need to seal the gutter that is leaking on 5. Chris will schedule them for later this week. We also need to get some siding to replace the wall they have been pulling off of in Building 10. | Need to get the siding to replenish the wall they have been pulling off of, also get them scheduled to start the punch work. | 2024-08-01 | Done
Pines @ Peach | Joe | Pristine |  |  | Outside of 3 done / Working on Outside of 2 - KMW has Pissed off the owners. Change order for Ceilings at top floors & Breezeways has been approved. 2 crews are working on re-insulating the windows on backside on buildings 3 and 2 Also have the same crews working on the breezeways Along with putting in flashing and 2x10 in place (flashing taped and flex taped all joints along with ty-vec work) (Porches are back flush on buildings 2 & 3) | CHANGE ORDERS??? |  | Done
Mountain Glen | Chris | Pristine / Rigo |  |  | Rigo was installing doors in the UFAS units, sample walls for siding have been hung on building 144 for viewing. Siding order will ship 12/3 and will arrive 12/5 - 12/6. Last truck of doors was delivered by Sik Sunday 12/1. Consolidate containers on site so that we have room to store our siding, and need to be prepared to unload siding when it arrives. | Need to find out what JGBR will be doing at Mountain Glen with Phillip, weather it is exterior work or interior work. Confirm if exterior doors are in the trailer Sik hauled up Sunday.
Holbrook | Chris | Pristine / Zavala |  |  | Zavala has his guys starting to felt Building 3 (Type 3). They have shingles on all amenities and garages. Building 2 also has shingles on it and now needs only the metal roofing. Jonathan also has sent us the material list for the metal he will be needing. | Call Jonathan, and make sure he has guys on site to unload truck of siding. (Carefully)
Dloniak House | Crawl Diddy | Pinnacle |  |  | Huntley - Bricking Chimney & House , PEM (plumbing)- waiting on tubs / (electrical) - lighting in kitchen and porches / (HVAC) - relocating lines & gas lines, Steve (Pro Chem) - after PME finished | Inspections? Getting tied into city- Hub cast iron? Gas Lines? Temp power? Structural Protection infront of plumbing fixtures in garages
Woodfield - BD3 | Joe |  |  |  | Should finish 3/7/25
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Aaron Mills | Chris | ? |  |  | Framing in Process
Jeffries -DHIC | Joe
Avonlea - DHIC | Joe
Sedgbrook - DHIC | Joe
Piney Pointe - BD3 | Joe
Brookside - BD3 | Joe
Woodfield - BD3 | Joe
Burnside - BD3 | Joe
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22 * *Again 10-23-24*
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 2-28-25
Team Meeting
2.28.25
Present: Wes, Oscar, Chris, Joe, Carson & Stephanie & Rebecca (Septet Team, PRESENT) - we need more space, more chairs
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Calendar - use to help track Change Order Work
3.) | Signed, CLOSING on Building for down the street
4.) | Review Employee P&P
5.)
6.)
7.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
8.) | Make sure all completed jobs are billed
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch lists for Building 7 & 8 are ready, still waiting on the list from HRP to close out 5 & 6. When we have Siks guys back out there they need to seal the gutter that is leaking on 5. Chris will schedule them for later this week. We also need to get some siding to replace the wall they have been pulling off of in Building 10. | Need to get the siding to replenish the wall they have been pulling off of, also get them scheduled to start the punch work. | 2024-08-01 | Done
Pines @ Peach | Joe | Pristine |  |  | Outside of 3 done / Working on Outside of 2 - KMW has Pissed off the owners. Change order for Ceilings at top floors & Breezeways has been approved. 2 crews are working on re-insulating the windows on backside on buildings 3 and 2 Also have the same crews working on the breezeways Along with putting in flashing and 2x10 in place (flashing taped and flex taped all joints along with ty-vec work) (Porches are back flush on buildings 2 & 3) | CHANGE ORDERS??? |  | Done
Mountain Glen | Chris | Pristine / Rigo |  |  | Rigo was installing doors in the UFAS units, sample walls for siding have been hung on building 144 for viewing. Siding order will ship 12/3 and will arrive 12/5 - 12/6. Last truck of doors was delivered by Sik Sunday 12/1. Consolidate containers on site so that we have room to store our siding, and need to be prepared to unload siding when it arrives. | Need to find out what JGBR will be doing at Mountain Glen with Phillip, weather it is exterior work or interior work. Confirm if exterior doors are in the trailer Sik hauled up Sunday.
Holbrook | Chris | Pristine / Zavala |  |  | Zavala has his guys starting to felt Building 3 (Type 3). They have shingles on all amenities and garages. Building 2 also has shingles on it and now needs only the metal roofing. Jonathan also has sent us the material list for the metal he will be needing. | Call Jonathan, and make sure he has guys on site to unload truck of siding. (Carefully)
Dloniak House | Crawl Diddy | Pinnacle |  |  | 3rd party Footing Inspection for Pinnacle Footers due to bad weather and emailed a copy of the Inspection to City of Greensboro (James Wolffe) / (Huntley Brothers) are wrapping up foundation perimeter (CMU block, brick and mortar) *Trash Dumpster is on site along with porty potty* CONTACTED Castro (framer) & Riverside Truss - Cliff (trusses) they want to meet 12/24 at 9AM and call Steve (Pro-Chem) for Termite spray before fondation inspection | HOA Approval for Shingle and Metal color / Cables at front of site need to be burried lower for driveway (Call contacts on email)
Woodfield - BD3 | Joe |  |  |  | Should finish 3/7/25
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Aaron Mills | Chris | ? |  |  | Framing in Process
Jeffries -DHIC | Joe
Avonlea - DHIC | Joe
Sedgbrook - DHIC | Joe
Piney Pointe - BD3 | Joe
Brookside - BD3 | Joe
Woodfield - BD3 | Joe
Burnside - BD3 | Joe
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22 * *Again 10-23-24*
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 12-2-24
Team Meeting
12.2.24
Present: Wes, Oscar, Chris, Joe, Carson & Stephanie (Seal Team 6, PRESENT)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Calendar - use to help track Change Order Work
3.) | Vehicles - keep oil changed, some inspections due 12/31 service truck
4.) | Contract log -Need - CO Pungo waiting on this, DHIC, Mountain Glen
5.) | Container lock keys on all vehicle key rings
6.) | Retail: please add address of work performed
7.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
8.) | Make sure all completed jobs are billed
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch lists for Building 7 & 8 are ready, still waiting on the list from HRP to close out 5 & 6. When we have Siks guys back out there they need to seal the gutter that is leaking on 5. Chris will schedule them for later this week. We also need to get some siding to replace the wall they have been pulling off of in Building 10. | Need to get the siding to replenish the wall they have been pulling off of, also get them scheduled to start the punch work. | 2024-08-01 | Done
KMW Townsend Trace | Chris |  |  |  | Gutter Repair, Rigo | Maybe this needs to be done on a Saturday |  | Done
Pines @ Peach | Joe | Pristine |  |  | Outside of 3 done / Working on Outside of 2 - KMW has Pissed off the owners. Change order for Ceilings at top floors & Breezeways has been approved. 2 crews are working on re-insulating the windows on backside on buildings 3 and 2 Also have the same crews working on the breezeways Along with putting in flashing and 2x10 in place (flashing taped and flex taped all joints along with ty-vec work) (Porches are back flush on buildings 2 & 3) | CHANGE ORDERS??? |  | Done
(KMW)Wakefield (5/2023) | Joe | Pristine |  |  | Pristine was to re-install the fence infront of building 2, needed to widen the fence. - OCN Dropped off grate and it fits perfectly inside building (Wes welded it) |  |  | Done
KMW Evoke | Chris | Rogelio/Hillstone |  |  | Rain delays for Hillstone. Rogelio work is change orders we will charge for. SA to send CO to Josh.
KMW Pungo | Joe | Pristine /Concrete Manuel |  |  | Want Stair rails done by wednsday, want to start ramp rails on Monday. Carson took trailer load of handrails 12/10/24 and Rogelio's crew was working on them this week. 12/18/24 Handrails were finished; Wes recieved messeages and pictures on handrails in place at 7pm. | Bank recieved photos of work.
Gatebay | Joe/ Chris | Pristine |  |  | Finished up, need to call in a final inspection to close out the permits in their system. Joe had gone back to install siding on the second shed there and job was closed up after that.
Mountain Glen | Chris | Pristine / Rigo |  |  | Rigo was installing doors in the UFAS units, sample walls for siding have been hung on building 144 for viewing. Siding order will ship 12/3 and will arrive 12/5 - 12/6. Last truck of doors was delivered by Sik Sunday 12/1. Consolidate containers on site so that we have room to store our siding, and need to be prepared to unload siding when it arrives. | Need to find out what JGBR will be doing at Mountain Glen with Phillip, weather it is exterior work or interior work. Confirm if exterior doors are in the trailer Sik hauled up Sunday.
Holbrook | Chris | Pristine / Zavala |  |  | Zavala has his guys starting to felt Building 3 (Type 3). They have shingles on all amenities and garages. Building 2 also has shingles on it and now needs only the metal roofing. Jonathan also has sent us the material list for the metal he will be needing. | Call Jonathan, and make sure he has guys on site to unload truck of siding. (Carefully)
Dloniak House | Crawl Diddy | Pinnacle |  |  | 3rd party Footing Inspection for Pinnacle Footers due to bad weather and emailed a copy of the Inspection to City of Greensboro (James Wolffe) / (Huntley Brothers) are wrapping up foundation perimeter (CMU block, brick and mortar) *Trash Dumpster is on site along with porty potty* CONTACTED Castro (framer) & Riverside Truss - Cliff (trusses) they want to meet 12/24 at 9AM and call Steve (Pro-Chem) for Termite spray before fondation inspection | HOA Approval for Shingle and Metal color / Cables at front of site need to be burried lower for driveway (Call contacts on email)
Charlotte Park |  |  |  |  | Bill to Evoke - Going to Fix Columns & Trim behind Meter box, dog wash
PartnShip - Parkview | Chris | [6 empty] | Cost Plus
Ridgeway BD3 | Chris | Zavala |  |  | Roofing for Building 5 & 6
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Aaron Mills | Chris | ? |  |  | Framing in Process
Jeffries -DHIC | Joe
Avonlea - DHIC | Joe
Sedgbrook - DHIC | Joe
Piney Pointe - BD3 | Joe
Brookside - BD3 | Joe
Woodfield - BD3 | Joe
Burnside - BD3 | Joe
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22 * *Again 10-23-24*
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 8-26-24
Team Meeting
8.26.24
Present: Wes, Oscar, Chris & Stephanie (the fab 4 all here)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Calendar - use to help track Change Order Work
3.) | Travis Fisher H&E Equipment Services
4.) | Contract log -Need - CO Pungo waiting on this, DHIC, Mountain Glen
5.) | Container lock keys on all vehicle key rings
6.) | Retail: please add address of work performed
7.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
8.) | Make sure all completed jobs are billed
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch list being completed, roof leaks being address, leak in clubhouse - Zavala to address when rain stop. Roofing to be picked up - Chris to have brought back to office, Oscar to call to pick up container once empty. |  | 2024-08-01 | Done
KMW Townsend Trace | Chris | [6 empty] | Done
Pines @ Peach | Chris | Pristine | Clubhouse | TBD after framing complete on bldg 3 | 7-29-24 - 1st truckloads arrived on site today, Chris went with Pristine to get them started to unload and staged. Flashing needs to be bent. Omar JR needs to give us the MF info.. - OCN |  |  | Done
(KMW)Wakefield (5/2023) | Chris |  |  |  | Pristine was to re-install the fence infront of building 2, needed to widen the fence. - OCN |  |  | Done
KMW Evoke | Chris | Rogelio/Hillstone |  |  | Rain delays for Hillstone. Rogelio work is change orders we will charge for. SA to send CO to Josh. | SA to enter CO for Rogelio work.
KMW Pungo | Chris | Pristine /Concrete Manuel |  |  | 7-29-24 - Rigo started to install Doors and trim in ADA units. we will need to get base trim from Lowes to complete. Need 4 Post for each rear deck
Gatebay | Chris |  |  |  | Oscar to sign contracts, Chris working on permits
Mountain Glen |  |  |  |  | Need contract, Oscar working on unit pricing-Wes & Chris going this week - Rigo there 8/26. Sik to do siding, skip breezeways
Holbrook
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Holbrook |  | Eldin????
Aaron Mills |  | ?
Mountain Glen - Brevard | Chris |  |  | Jason Buffkin | 8-5-24 - Want to start demo in closets, need contract! - OCN
Gatebay I&II |  |  |  |  | 7-29-24 We have contracts for siding and 6 doors. Dont have windows? Still waiting to see what Frankie has to say. - OCN
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
Mountain Glen - Brevard |  |  |  |  | Re-Estimating, Should start after Pungo, Maybe August? - OCN
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 8-8-24
Team Meeting
08.08.24
Present: Wes, Oscar, Chris & Stephanie (the fab 4 all here)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Calendar - use to help track Change Order Work
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log -Need - CO Pungo waiting on this, DHIC, Mountain Glen
5.) | Container lock keys on all vehicle key rings
6.) | Retail: please add address of work performed
7.) | Reminder - Add notes in memo line of estimate/CO emailed to customer
8.) | Make sure all completed jobs are billed
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Punch list being completed, roof leaks being address, leak in clubhouse - Zavala to address when rain stop. Roofing to be picked up - Chris to have brought back to office, Oscar to call to pick up container once empty. |  | 2024-08-01 | Done
KMW Townsend Trace | Chris | [6 empty] | Done
Pines @ Peach | Chris | Pristine | Clubhouse | TBD after framing complete on bldg 3 | 7-29-24 - 1st truckloads arrived on site today, Chris went with Pristine to get them started to unload and staged. Flashing needs to be bent. Omar JR needs to give us the MF info.. - OCN |  |  | Done
(KMW)Wakefield (5/2023) | Chris |  |  |  | Pristine was to re-install the fence infront of building 2, needed to widen the fence. - OCN |  |  | Done
KMW Evoke | Chris | Rogelio/Hillstone |  |  | Rain delays for Hillstone. Rogelio work is change orders we will charge for. SA to send CO to Josh. | SA to enter CO for Rogelio work.
KMW Pungo | Chris | Pristine /Concrete Manuel |  |  | 7-29-24 - Rigo started to install Doors and trim in ADA units. we will need to get base trim from Lowes to complete. Need 4 Post for each rear deck
Gatebay | Chris |  |  |  | Oscar to sign contracts, Chris working on permits
Mountain Glen |  |  |  |  | Need contract, Oscar working on unit pricing
Holbrook
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Holbrook |  | Eldin????
Aaron Mills |  | ?
Mountain Glen - Brevard | Chris |  |  | Jason Buffkin | 8-5-24 - Want to start demo in closets, need contract! - OCN
Gatebay I&II |  |  |  |  | 7-29-24 We have contracts for siding and 6 doors. Dont have windows? Still waiting to see what Frankie has to say. - OCN
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
Mountain Glen - Brevard |  |  |  |  | Re-Estimating, Should start after Pungo, Maybe August? - OCN
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 7-29-24
Team Meeting
07.29.24
Present: Wes, Oscar, Chris & Stephanie (the fab 4 all here)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Started meeting at pm
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.)
6.)
7.) | Make sure all completed jobs are billed
8.)
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine | [5 empty] | Done
KMW Townsend Trace | Chris | ELV |  |  | 7-26-29 - Chris and Oscar picked up some left over material. Will still need said material for punch work, still waiting on siding to show up @ ABC so punch can be completed. - OCN |  |  | Done
Pines @ Peach | Chris | Pristine / Rogelio |  |  | 7-29-24 - 1st truckloads arrived on site today, Chris went with Pristine to get them started to unload and staged. Flashing needs to be bent. Omar JR needs to give us the MF info.. - OCN
(KMW)Wakefield (5/2023) | Chris | Pristine |  |  | 7-29-24 - Pristine was to re-install the fence infront of building 2, needed to widen the fence. - OCN |  |  | Done
KMW Evoke | Chris | Towa / Rogelio
KMW Pungo | Chris | Pristine / Rogelio / Concrete Manuel |  |  | 7-29-24 - Rigo started to install Doors and trim in ADA units. we will need to get base trim from Lowes to complete. Need 4 Post for each rear deck
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  | Customer Contact | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Holbrook |  | Eldin????
Aaron Mills |  | ?
Mountain Glen - Brevard | Chris |  |  | Jason Buffkin | 8-5-24 - Want to start demo in closets, need contract! - OCN
Gatebay I&II |  |  |  |  | 7-29-24 We have contracts for siding and 6 doors. Dont have windows? Still waiting to see what Frankie has to say. - OCN
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
Mountain Glen - Brevard |  |  |  |  | Re-Estimating, Should start after Pungo, Maybe August? - OCN
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Working on revised plans.

## 7-11-24
Team Meeting
07.11.24
Present: Wes, Oscar, Chris & Stephanie (the fab 4 all here)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Started meeting at 3:35 am
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.)
6.)
7.) | Make sure all completed jobs are billed
8.)
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine | [5 empty] | Done
KMW Townsend Trace | Chris | ELV | [5 empty] | Done
Pines @ Peach | Chris | Pristine / Rogelio
(KMW)Wakefield (5/2023) | Chris | Pristine | [5 empty] | Done
KMW Evoke | Chris | Towa / Rogelio
KMW Pungo | Chris | Pristine / Rogelio
HRP Pine Forest | Chris | Pristine
HRP Weaverville | Chris | Towa
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Holbrook |  | Eldin???? |  |  | Should poured concrete for clubhous this week - OCN
Aaron Mills |  | ? |  |  | Awarded, Will start working on initial setup - OCN
Mountain Glen - Brevard | Chris |  |  | Jason Buffkin | Wes/Chris/Rigo going to reframe an HVAC closet
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
Mountain Glen - Brevard |  |  |  |  | Re-Estimating, Should start after Pungo, Maybe August? - OCN
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.

## 6-7-24
Team Meeting
06.7.24
Present: Wes, Oscar, Chris (the fab 4 minus Stephanie)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Started meeting at 10:15am, Ended very fast, Restarted with Andy's around 3pm
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.)
6.)
7.) | Make sure all completed jobs are billed
8.)
PROJECTS
Current Projects (Start Date) | Project Manager (always Chris) | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023) | Chris | Pristine |  |  | Currently on 9,10, breezeways in 7. Some Fiber Cement on 11 started - OCN |  |  | Done
KMW Townsend Trace | Chris | ELV |  |  | Almost finished, Rogelio cleaning out materials in containers. Taking back to ABC - OCN |  |  | Done
(KMW)Wakefield (5/2023) | Chris | Pristine |  |  | Punch work - OCN |  |  | Done
KMW Evoke | Chris | Towa / Rogelio |  |  | Monday/Tuesday Rails - OCN
KMW Pungo | Chris | Pristine / Rogelio |  |  | Send Rogelio to possibly do trim around doors in laundries Behind MF's- Wednesday? possibly go on the 17th. But if Traco goes faster, we could go Wednesday(12th) - OCN
HRP Pine Forest | Chris | Pristine |  |  | Siki repairing B&B - OCN
Jerrets house | Chris | Towa |  |  | Rigo did Gutters 6-6-24 - OCN
HRP Weaverville | Chris | Towa |  |  | Needs to fix what he did or didnt do - OCN
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Holbrook |  | Eldin???? |  |  | Should poured concrete for clubhous this week - OCN
Pines @ Peach | Chris | Pristine / Rogelio |  |  | Hardie material was sent to contract, writing contract for Prestine, building Truck Builder. Need to set up "Project" - OCN | Writing up contract,
Aaron Mills |  | ? |  |  | Awarded, Will start working on initial setup - OCN
Mountain Glen - Brevard | Chris |  |  | Jason Buffkin | Re-Estimating, Should start after Pungo, Maybe August? -OCN
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Resent Estimate on 5-28-24 - OCN
PPM-Kings Crossing | Not KW |  |  | Buffkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Buffkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
Mountain Glen - Brevard |  |  |  |  | Re-Estimating, Should start after Pungo, Maybe August? - OCN
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Buffkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Buffkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Buffkin | Storage room doors, roof replacement, siding pricing per building
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Buffkin
HRP Murrayville
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.

## 4-26-24
Team Meeting
04.26.24
Present: Wes, Oscar, Chris & Liam (the fab 4 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Started meeting at 8:10am
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.)
6.)
7.) | Make sure all completed jobs are billed
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023)
KMW Townsend Trace | Matt | Pato
(KMW)Wakefield (5/2023) |  | Tulio
KMW Pungo |  | Sik, Rogelio
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Wes
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
KMW Pines @ Peach Rd |  |  |  |  | Estimate revised *OCN 1-6-23 | Wes submitting. Due 1-9-23
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Evolve @ North Shore |  |  |  |  | working on quote
Evolve @ Headwaters |  |  |  |  | working on quote
Evovle @ Northwest |  |  |  |  | working on quote
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Waiting on payment for completed work in Sept. '22. No future jobs scheduled.
SC Hail Job

## 9-22-23
Team Meeting
09.08.23
Present: Wes, Oscar & Matt (the fab 3 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Started meeting at 8:15am
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.)
6.)
7.) | Make sure all completed jobs are billed
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023)
KMW Townsend Trace | Matt | Pato |  |  | Started on Clubhouse & Bld 1 9-21-23
(KMW)Wakefield (5/2023) |  | Tulio
KMW Leo Loso/Gateway @ CLT Park $$$
KMW Springfield
HRP Waterway
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Wes
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
KMW Pines @ Peach Rd |  |  |  |  | Estimate revised *OCN 1-6-23 | Wes submitting. Due 1-9-23
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Evolve @ North Shore |  |  |  |  | working on quote
Evolve @ Headwaters |  |  |  |  | working on quote
Evovle @ Northwest |  |  |  |  | working on quote
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Waiting on payment for completed work in Sept. '22. No future jobs scheduled.
SC Hail Job

## 9-8-23
Team Meeting
09.08.23
Present: Wes, Oscar & Matt (the fab 3 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Started meeting at 10:30am, Stephanie M.I.A - showed up late, at 10:45am and left at 10:55am. 10:56am Wes told Steph to GTFO
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.)
6.)
7.) | Make sure all completed jobs are billed
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Brightwood (4/2023)
KMW Townsend Trace
(KMW)Wakefield (5/2023)
KMW Leo Loso/Gateway @ CLT Park $$$
KMW Springfield
HRP Waterway
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
Wes
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
KMW Pines @ Peach Rd |  |  |  |  | Estimate revised *OCN 1-6-23 | Wes submitting. Due 1-9-23
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Evolve @ North Shore |  |  |  |  | working on quote
Evolve @ Headwaters |  |  |  |  | working on quote
Evovle @ Northwest |  |  |  |  | working on quote
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Waiting on payment for completed work in Sept. '22. No future jobs scheduled.
SC Hail Job

## 7-27-23
Team Meeting
6.29.23
Present: Wes, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 4 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.) | Wesco 2016 Service truck. Inspection done 1-19-23 . Needs tires and brakes
6.) | Wes' 2019 at Randy Marion Chevy in Statesville. Will have oil change, and inspection if needed. Possibly new tires while its there.
7.) | Make sure all completed jobs are billed (Burlington Job) We should have at least partial billed this if roofing was going to be this far out from being done.
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes/Oscar | Bruzz / Pato |  | 2023-01-27 | There is 100+ squares of siding coming in (Friday Feb 3rd that will need to be picked up/delivered to office) and delivered up to Asheville Monday Feb. 6th for Pato to start siding. Rigo may need to be there this week if available to do a little punch work. Otherwise Bruzz can do if need be. | Get gutter material out of conex. Lets try to get rid of one of these conex's next week. (2-6-23) Need to make sure Pato has updated Insurance**Asked for updated insurance, their agent should be sending it over to us. OCN 2/3/23 **Lansing has a delay for siding, they are sendnig a truck up to Winchester VA to pick it up, and will try to deliver it to us Monday afternoon.** OCN 2-3-23 | 2023-02-28 | Zavala contract executed - Villeda need to see if in service truck
HRP Pine Forest II | Wes /CJ |  |  | 2023-01-27 | Samir is more than likely going to finish rest of project. I would say about 3 weeks. Need to get rest of shake material on the job and probably more solid soffit for breezeways. Need to confirm and get on job if necessary. | Get gutter material inventory on job. Lansing should have remainder
KMW Church St Lofts (4/2022) | SJH |  |  |  | Rigo at Church Street for week of 1/30-2/3 to complete scope of work, Change Orders, and punch list.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes/Sam | Rogelio 4/13 | Cipriano June-August |  | Need to make sure left side of building 2 is finished. Need to get columns started and balconies finished. Where are we with Tiger Wood? Need to start moving materials off building 3 pad. Josh Has not yet submitted approval for use of the 4x4 posts in lieu of the steel posts. SH to follow up with Josh first thing on 1/30/23. | SH sent email to J. Blevins on morning of 1/30/23. Will follow up by 1/31/23 if response is not received.
KMW Retreat $$$ | Wes | Rogelio/Cipriano | 2023-02-04 |  | Rogelio and Cipriano are there finishing BS for KMW. Wes needs to get CO list together. |  | 2022-08-15
KMW Springfield | SJH |  |  |  | Manuel working on finishing last of initial push units. Should be completed by 2/1 or 2/2. Second push to begin immediately following - to include installation of windows, doors, door and bath hardware. ANTWAN WANTS TWO CREWS THERE FOR THIS PART IF POSSIBLE. |  | 2023-02-28
St. Marks | SJH |  |  |  | Jonathan completed final metal roofs - SH to visit site on 1/30 or 1/31 to walk last building to comfirm completion. Caleb says everything is done, but need to verify.
HRP Waterway | Wes/CJ | Samir |  |  | CJ this is for you! Get inspections on the Machines, and find someone local to work on them. Thanks Oscar | Need subcontract for Samir*?? Has this been done CJ??
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Carlos checking on final pricing for masonry repair. SH to give PPM price on interior repair completion outside of masonry repairs. SH will have estimate to PM by 1/31/23. Will pull permits and schedule repair work pending approval by PPM. | Talked to Carlos on 1/31/23. He hopes to have his pricing back by 1/31/23-2/1/23 - SJH
Springbranch - Becon (Wilmington, NC) | Wes/Oscar | Rogelio/Rigo |  |  | Oscar - Alside's ship date is Feb13th / Maintenace wants to know if they need access inside the units or not, said last time they were able to do everything from outside. | Waiting for confirmation for materials to arrive.
111 Tarpley St. | SJH | El Bruzz, Zavala |  |  | Zavala installing roof morning of 1/30/23. Gutters to be installed as soon as weather permits. Invoice to be sent the same day gutters are completed |  | 2023-02-08
PPM - Wind Ridge |  |  |  | Jason Buffkin | Need (4) columns installed and beam wrapped on front porch. Can El Bruzz or Pato do this while at Haywood? Yes |  | 2/3/23?
PPM - Rocky Knoll | SJH |  |  |  | Unit 1G - Campbell electric to complete electrical repairs on 1/30/23. SH to confirm completion by end of day 1/30. Return to unit on Wednesday, 2/1/23 to install drywall and cabinets. **Working on schedule with trades to complete unit 1C.
Melanie's House |  |  |  |  | Plumbing? Insulation? When to deliver Drywall? | Oscar has Hanger and Finisher lined up.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
KMW Townsend Trace | Wes
(KMW)Wakefield (5/2023) | Sam |  |  |  | Lets get material list together. Need to order around 3-15-23
Ariston Place - Windsor | Wes |  |  |  | We need to get samples submitted. See email from Windsor | Get samples, a piece of each color cut in half, panels
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
KMW Pines @ Peach Rd |  |  |  |  | Estimate revised *OCN 1-6-23 | Wes submitting. Due 1-9-23
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Evolve @ North Shore |  |  |  |  | working on quote
Evolve @ Headwaters |  |  |  |  | working on quote
Evovle @ Northwest |  |  |  |  | working on quote
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Waiting on payment for completed work in Sept. '22. No future jobs scheduled.
SC Hail Job

## 6-29-23
Team Meeting
6.29.23
Present: Wes, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 4 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.) | Wesco 2016 Service truck. Inspection done 1-19-23 . Needs tires and brakes
6.) | Wes' 2019 at Randy Marion Chevy in Statesville. Will have oil change, and inspection if needed. Possibly new tires while its there.
7.) | Make sure all completed jobs are billed (Burlington Job) We should have at least partial billed this if roofing was going to be this far out from being done.
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes/Oscar | Bruzz / Pato |  | 2023-01-27 | There is 100+ squares of siding coming in (Friday Feb 3rd that will need to be picked up/delivered to office) and delivered up to Asheville Monday Feb. 6th for Pato to start siding. Rigo may need to be there this week if available to do a little punch work. Otherwise Bruzz can do if need be. | Get gutter material out of conex. Lets try to get rid of one of these conex's next week. (2-6-23) Need to make sure Pato has updated Insurance**Asked for updated insurance, their agent should be sending it over to us. OCN 2/3/23 **Lansing has a delay for siding, they are sendnig a truck up to Winchester VA to pick it up, and will try to deliver it to us Monday afternoon.** OCN 2-3-23 | 2023-02-28 | Zavala contract executed - Villeda need to see if in service truck
HRP Pine Forest II | Wes /CJ |  |  | 2023-01-27 | Samir is more than likely going to finish rest of project. I would say about 3 weeks. Need to get rest of shake material on the job and probably more solid soffit for breezeways. Need to confirm and get on job if necessary. | Get gutter material inventory on job. Lansing should have remainder
KMW Church St Lofts (4/2022) | SJH |  |  |  | Rigo at Church Street for week of 1/30-2/3 to complete scope of work, Change Orders, and punch list.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes/Sam | Rogelio 4/13 | Cipriano June-August |  | Need to make sure left side of building 2 is finished. Need to get columns started and balconies finished. Where are we with Tiger Wood? Need to start moving materials off building 3 pad. Josh Has not yet submitted approval for use of the 4x4 posts in lieu of the steel posts. SH to follow up with Josh first thing on 1/30/23. | SH sent email to J. Blevins on morning of 1/30/23. Will follow up by 1/31/23 if response is not received.
KMW Retreat $$$ | Wes | Rogelio/Cipriano | 2023-02-04 |  | Rogelio and Cipriano are there finishing BS for KMW. Wes needs to get CO list together. |  | 2022-08-15
KMW Springfield | SJH |  |  |  | Manuel working on finishing last of initial push units. Should be completed by 2/1 or 2/2. Second push to begin immediately following - to include installation of windows, doors, door and bath hardware. ANTWAN WANTS TWO CREWS THERE FOR THIS PART IF POSSIBLE. |  | 2023-02-28
St. Marks | SJH |  |  |  | Jonathan completed final metal roofs - SH to visit site on 1/30 or 1/31 to walk last building to comfirm completion. Caleb says everything is done, but need to verify.
HRP Waterway | Wes/CJ | Samir |  |  | CJ this is for you! Get inspections on the Machines, and find someone local to work on them. Thanks Oscar | Need subcontract for Samir*?? Has this been done CJ??
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Carlos checking on final pricing for masonry repair. SH to give PPM price on interior repair completion outside of masonry repairs. SH will have estimate to PM by 1/31/23. Will pull permits and schedule repair work pending approval by PPM. | Talked to Carlos on 1/31/23. He hopes to have his pricing back by 1/31/23-2/1/23 - SJH
Springbranch - Becon (Wilmington, NC) | Wes/Oscar | Rogelio/Rigo |  |  | Oscar - Alside's ship date is Feb13th / Maintenace wants to know if they need access inside the units or not, said last time they were able to do everything from outside. | Waiting for confirmation for materials to arrive.
111 Tarpley St. | SJH | El Bruzz, Zavala |  |  | Zavala installing roof morning of 1/30/23. Gutters to be installed as soon as weather permits. Invoice to be sent the same day gutters are completed |  | 2023-02-08
PPM - Wind Ridge |  |  |  | Jason Buffkin | Need (4) columns installed and beam wrapped on front porch. Can El Bruzz or Pato do this while at Haywood? Yes |  | 2/3/23?
PPM - Rocky Knoll | SJH |  |  |  | Unit 1G - Campbell electric to complete electrical repairs on 1/30/23. SH to confirm completion by end of day 1/30. Return to unit on Wednesday, 2/1/23 to install drywall and cabinets. **Working on schedule with trades to complete unit 1C.
Melanie's House |  |  |  |  | Plumbing? Insulation? When to deliver Drywall? | Oscar has Hanger and Finisher lined up.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date | Shits going to hit the fan, it is for sure! Bruh
HRP Brightwood (4/2023)
KMW Townsend Trace | Wes
(KMW)Wakefield (5/2023) | Sam |  |  |  | Lets get material list together. Need to order around 3-15-23
Ariston Place - Windsor | Wes |  |  |  | We need to get samples submitted. See email from Windsor | Get samples, a piece of each color cut in half, panels
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
KMW Pines @ Peach Rd |  |  |  |  | Estimate revised *OCN 1-6-23 | Wes submitting. Due 1-9-23
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Evolve @ North Shore |  |  |  |  | working on quote
Evolve @ Headwaters |  |  |  |  | working on quote
Evovle @ Northwest |  |  |  |  | working on quote
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Waiting on payment for completed work in Sept. '22. No future jobs scheduled.
SC Hail Job

## 4-3-23
Team Meeting
4.3.23
Present: Wes, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 4 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.) | Wesco 2016 Service truck. Inspection done 1-19-23 . Needs tires and brakes
6.) | Wes' 2019 at Randy Marion Chevy in Statesville. Will have oil change, and inspection if needed. Possibly new tires while its there.
7.) | Make sure all completed jobs are billed (Burlington Job) We should have at least partial billed this if roofing was going to be this far out from being done.
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes/Oscar | Bruzz / Pato |  | 2023-01-27 | There is 100+ squares of siding coming in (Friday Feb 3rd that will need to be picked up/delivered to office) and delivered up to Asheville Monday Feb. 6th for Pato to start siding. Rigo may need to be there this week if available to do a little punch work. Otherwise Bruzz can do if need be. | Get gutter material out of conex. Lets try to get rid of one of these conex's next week. (2-6-23) Need to make sure Pato has updated Insurance**Asked for updated insurance, their agent should be sending it over to us. OCN 2/3/23 **Lansing has a delay for siding, they are sendnig a truck up to Winchester VA to pick it up, and will try to deliver it to us Monday afternoon.** OCN 2-3-23 | 2023-02-28 | Zavala contract executed - Villeda need to see if in service truck
HRP Pine Forest II | Wes /CJ |  |  | 2023-01-27 | Samir is more than likely going to finish rest of project. I would say about 3 weeks. Need to get rest of shake material on the job and probably more solid soffit for breezeways. Need to confirm and get on job if necessary. | Get gutter material inventory on job. Lansing should have remainder
KMW Church St Lofts (4/2022) | SJH |  |  |  | Rigo at Church Street for week of 1/30-2/3 to complete scope of work, Change Orders, and punch list.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes/Sam | Rogelio 4/13 | Cipriano June-August |  | Need to make sure left side of building 2 is finished. Need to get columns started and balconies finished. Where are we with Tiger Wood? Need to start moving materials off building 3 pad. Josh Has not yet submitted approval for use of the 4x4 posts in lieu of the steel posts. SH to follow up with Josh first thing on 1/30/23. | SH sent email to J. Blevins on morning of 1/30/23. Will follow up by 1/31/23 if response is not received.
KMW Retreat $$$ | Wes | Rogelio/Cipriano | 2023-02-04 |  | Rogelio and Cipriano are there finishing BS for KMW. Wes needs to get CO list together. |  | 2022-08-15
KMW Springfield | SJH |  |  |  | Manuel working on finishing last of initial push units. Should be completed by 2/1 or 2/2. Second push to begin immediately following - to include installation of windows, doors, door and bath hardware. ANTWAN WANTS TWO CREWS THERE FOR THIS PART IF POSSIBLE. |  | 2023-02-28
St. Marks | SJH |  |  |  | Jonathan completed final metal roofs - SH to visit site on 1/30 or 1/31 to walk last building to comfirm completion. Caleb says everything is done, but need to verify.
HRP Waterway | Wes/CJ | Samir |  |  | CJ this is for you! Get inspections on the Machines, and find someone local to work on them. Thanks Oscar | Need subcontract for Samir*?? Has this been done CJ??
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Carlos checking on final pricing for masonry repair. SH to give PPM price on interior repair completion outside of masonry repairs. SH will have estimate to PM by 1/31/23. Will pull permits and schedule repair work pending approval by PPM. | Talked to Carlos on 1/31/23. He hopes to have his pricing back by 1/31/23-2/1/23 - SJH
Springbranch - Becon (Wilmington, NC) | Wes/Oscar | Rogelio/Rigo |  |  | Oscar - Alside's ship date is Feb13th / Maintenace wants to know if they need access inside the units or not, said last time they were able to do everything from outside. | Waiting for confirmation for materials to arrive.
111 Tarpley St. | SJH | El Bruzz, Zavala |  |  | Zavala installing roof morning of 1/30/23. Gutters to be installed as soon as weather permits. Invoice to be sent the same day gutters are completed |  | 2023-02-08
PPM - Wind Ridge |  |  |  | Jason Buffkin | Need (4) columns installed and beam wrapped on front porch. Can El Bruzz or Pato do this while at Haywood? Yes |  | 2/3/23?
PPM - Rocky Knoll | SJH |  |  |  | Unit 1G - Campbell electric to complete electrical repairs on 1/30/23. SH to confirm completion by end of day 1/30. Return to unit on Wednesday, 2/1/23 to install drywall and cabinets. **Working on schedule with trades to complete unit 1C.
Melanie's House |  |  |  |  | Plumbing? Insulation? When to deliver Drywall? | Oscar has Hanger and Finisher lined up.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date | Shits going to hit the fan, it is for sure! Bruh
HRP Brightwood (4/2023)
KMW Townsend Trace | Wes
(KMW)Wakefield (5/2023) | Sam |  |  |  | Lets get material list together. Need to order around 3-15-23
Ariston Place - Windsor | Wes |  |  |  | We need to get samples submitted. See email from Windsor | Get samples, a piece of each color cut in half, panels
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
KMW Pines @ Peach Rd |  |  |  |  | Estimate revised *OCN 1-6-23 | Wes submitting. Due 1-9-23
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Evolve @ North Shore |  |  |  |  | working on quote
Evolve @ Headwaters |  |  |  |  | working on quote
Evovle @ Northwest |  |  |  |  | working on quote
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Waiting on payment for completed work in Sept. '22. No future jobs scheduled.
SC Hail Job

## 1.30.23
Team Meeting
1.30.23
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.) | Wesco 2016 Service truck. Inspection done 1-19-23 . Needs tires and brakes
6.) | Wes' 2019 at Randy Marion Chevy in Statesville. Will have oil change, and inspection if needed. Possibly new tires while its there.
7.) | Make sure all completed jobs are billed (Burlington Job) We should have at least partial billed this if roofing was going to be this far out from being done.
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes/Oscar | Bruzz / Pato |  | 2023-01-27 | Material is ordered to finish the last building. There is 10 boxes of j channel onsite and 2 more boxes at Lansing. There is 100+ squares of siding coming in (Friday Feb 3rd that will need to be picked up/delivered to office) and delivered up to Asheville Monday Feb. 6th for Pato to start siding. Rigo may need to be there this week if available to do a little punch work. Otherwise Bruzz can do if need be. | Get gutter material out of conex. Lets try to get rid of one of these conex's next week. (1-30-23) Need to make sure Pato has updated Insurance** | 2023-02-28 | Zavala contract executed - Villeda need to see if in service truck
HRP Pine Forest II | Wes /CJ |  |  | 2023-01-27 | Samir is more than likely going to finish rest of project. I would say about 3 weeks. Need to get rest of shake material on the job and probably more solid soffit for breezeways. Need to confirm and get on job if necessary. | Get gutter material inventory on job. Lansing should have remainder
KMW Church St Lofts (4/2022) | SJH |  |  |  | Rigo at Church Street for week of 1/30-2/3 to complete scope of work, Change Orders, and punch list.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes/Sam | Rogelio 4/13 | Cipriano June-August |  | Need to make sure left side of building 2 is finished. Need to get columns started and balconies finished. Where are we with Tiger Wood? Need to start moving materials off building 3 pad. Josh Has not yet submitted approval for use of the 4x4 posts in lieu of the steel posts. SH to follow up with Josh first thing on 1/30/23. | SH sent email to J. Blevins on morning of 1/30/23. Will follow up by 1/31/23 if response is not received.
KMW Retreat $$$ | Wes | Rogelio/Cipriano | 2023-02-04 |  | Rogelio and Cipriano are there finishing BS for KMW. Wes needs to get CO list together. |  | 2022-08-15
KMW Springfield | SJH |  |  |  | Manuel working on finishing last of initial push units. Should be completed by 2/1 or 2/2. Second push to begin immediately following - to include installation of windows, doors, door and bath hardware. ANTWAN WANTS TWO CREWS THERE FOR THIS PART IF POSSIBLE. |  | 2023-02-28
St. Marks | SJH |  |  |  | Jonathan completed final metal roofs - SH to visit site on 1/30 or 1/31 to walk last building to comfirm completion. Caleb says everything is done, but need to verify.
HRP Waterway | Wes/CJ | Samir |  |  | CJ this is for you! Get inspections on the Machines, and find someone local to work on them. Thanks Oscar | Need subcontract for Samir*
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Carlos checking on final pricing for masonry repair. SH to give PPM price on interior repair completion outside of masonry repairs. SH will have estimate to PM by 1/31/23. Will pull permits and schedule repair work pending approval by PPM. | Talked to Carlos on 1/31/23. He hopes to have his pricing back by 1/31/23-2/1/23 - SJH
Springbranch - Becon (Wilmington, NC) | Wes/Oscar | Rogelio/Rigo |  |  | Please let maintence know what ship dates are. Oscar - Need contact info for maintenace, Alside's ship date is Feb13th | Waiting for confirmation for materials to arrive.
111 Tarpley St. | SJH | El Bruzz, Zavala |  |  | Zavala installing roof morning of 1/30/23. Gutters to be installed as soon as weather permits. Invoice to be sent the same day gutters are completed |  | 2023-02-08
PPM - Wind Ridge |  |  |  | Jason Buffkin | Need (4) columns installed and beam wrapped on front porch. Can El Bruzz or Pato do this while at Haywood? Yes |  | 2/3/23?
PPM - Rocky Knoll | SJH |  |  |  | Unit 1G - Campbell electric to complete electrical repairs on 1/30/23. SH to confirm completion by end of day 1/30. Return to unit on Wednesday, 2/1/23 to install drywall and cabinets. **Working on schedule with trades to complete unit 1C.
Melanie's House |  |  |  |  | Plumbing? Insulation? When to deliver Drywall? | Oscar has Hanger and Finisher lined up.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date | Shits going to hit the fan, it is for sure! Bruh
HRP Brightwood (4/2023)
KMW Townsend Trace | Wes
(KMW)Wakefield (4/2023) | Sam |  |  |  | Lets get material list together. Need to order around 3-15-23
Ariston Place - Windsor | Wes |  |  |  | We need to get samples submitted. See email from Windsor | Get samples, a piece of each color cut in half, panels
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
KMW Pines @ Peach Rd |  |  |  |  | Estimate revised *OCN 1-6-23 | Wes submitting. Due 1-9-23
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Evolve @ North Shore |  |  |  |  | working on quote
Evolve @ Headwaters |  |  |  |  | working on quote
Evovle @ Northwest |  |  |  |  | working on quote
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Waiting on payment for completed work in Sept. '22. No future jobs scheduled.
SC Hail Job

## 1.6.23
Team Meeting
1.6.23
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today even though she is in an exam) and The Prince(the fab 5 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.)
6.) | Vehicle Inspections 1998 GMC, 2007 Chevy, Service Truck, Wes
7.) | Christmas
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Manuel installed handrails on bldg 2 breezeways on 10/17. Waiting on bldgs 1 & 3 to be ready to install breezeway siding and soffit. *SJH - 10/19/22 |  | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Remaining metal roofing order delivered on Tuesday, 8/30/22. Roofers began installing shingles on bldg 4 and metal on all bldgs. Zavala's measurements and quantities were incorrect - please see action items to the right. *SJH 9/6/22 | Supplementary metal to be picked up between 9/8-9/9. Wes/CJ to take it if it arrives on 9/8, SJH to take it if it arrives on 9/9. *SJH 9/8/22
KMW Church St Lofts (4/2022) | SJH |  |  |  | TKG working on installing corridor base and handrails backing, exterior and storage doors throughout the rest of the building, and hardware kits for units that are ready. *SJH - 10/19/22 | Stay up to date on drywall progress.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Cipriano working on courtyard of #2 until the weekend of 10/21, then he's moving to the outside of the building while grading and pool are installed. Hardie truck #11 scheduled for delivery on 10/20/22. Caulk delivered by SJH on 10/14. EZ.21 truck delivery is still en route, no tracking is available and they can't give us any more information on the driver's progress. *SJH - 10/19/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse $80K profit - why? missing/miscoded invoices? Extra profit is from bathroom hardware order (not yet placed to save space in shop - pricing held on quote from HD Supply) *SJH - 10/19/22 | Jason B. & Kyle M. Say that the job is likely to CLOSE in October, with work beginning in November. Still no confirmation on start date from KMW - *SJH - 10/19/22
St. Marks | SJH |  |  |  | CO for storage fees approved and charged. Still no definite date on completion of breezeway gypcrete, but Caleb says the building should be ready for us "in two weeks". They have asked us to install gutters on #5 & Pool house ASAP - Rigo might be able to go as early as 10/20/22. *SJH - 10/19/22 | Potential future job - vinyl ceilings in breezeways. Nothing new as of 9/2/22. No decision has been made here yet. *Caleb still doesn't have answer on this - it is not likely that this will be awarded at this point since the property is selling in a few weeks. *SJH - 10/19/22
HRP Waterway |  | Samir |  |  | First 5 Truckloads have been delivered, Next 9 Trucks should arrive on or before 11/29. Also Ordered Breezeway Solid Soffit from Alside. *OCN 10/19/22. Need subcontract agreements - Samir - Hardie picking up 320 of 5/4x12 *OCN 11/10/22 | Need subcontract for Samir*
Carlisle Reno |  |  |  |  | Job is completed and invoice was sent a month ago. Waiting on payment to be made. *SJH - 10/19/22
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Manuel making corrections to framing repairs, reinstalling jack posts as permanent fixtures with (3) 2x8 beam, installing drywall and getting ready for final inspections. At current pace, Manuel should finish with work on 10/20 or 10/21. Final inspections to be performed at beginning of following week based on inspectors availability. *SJH - 10/19/22 | Sam working with engineer to get pricing together for recently damaged exterior wall. Engineer is to submit repair plan for review on 10/19/22. *SJH - 10/19/22
Springbranch - Becon (Wilmington, NC) | Wes | Rogelio/Rigo |  |  | Replace 60 sashes | Waiting for confirmation for materials to arrive.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (4/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Melanie Combs house
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Get pricing together to complete panel replacement. *SJH - 10/19/22
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
KMW Pines @ Peach Rd |  |  |  |  | Estimate revised *OCN 1-6-23 | Wes submitting. Due 1-9-23
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ariston Place - Windsor |  |  |  |  | Awaiting Subcontract *OCN 10/26/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | All currently awarded work has been completed. Property is working through budgets to approve outstanding quotes.
SC Hail Job

## 12.16.22
Team Meeting
12.16.22
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today even though she is in an exam) and The Prince(the fab 5 All HERE)
Topics
1.) | Weekly: Sub calendar update/Daily Job Sheets/Photos Uploaded
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | PO - PM to enter prior to job start; note if it is a subcategory of a job the name doesn't feed down BOLO for this
4.) | Contract log
5.)
6.) | Vehicle Inspections 1998 GMC, 2007 Chevy, Service Truck, Wes
7.) | Christmas
8.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Manuel installed handrails on bldg 2 breezeways on 10/17. Waiting on bldgs 1 & 3 to be ready to install breezeway siding and soffit. *SJH - 10/19/22 |  | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Remaining metal roofing order delivered on Tuesday, 8/30/22. Roofers began installing shingles on bldg 4 and metal on all bldgs. Zavala's measurements and quantities were incorrect - please see action items to the right. *SJH 9/6/22 | Supplementary metal to be picked up between 9/8-9/9. Wes/CJ to take it if it arrives on 9/8, SJH to take it if it arrives on 9/9. *SJH 9/8/22
KMW Church St Lofts (4/2022) | SJH |  |  |  | TKG working on installing corridor base and handrails backing, exterior and storage doors throughout the rest of the building, and hardware kits for units that are ready. *SJH - 10/19/22 | Stay up to date on drywall progress.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Cipriano working on courtyard of #2 until the weekend of 10/21, then he's moving to the outside of the building while grading and pool are installed. Hardie truck #11 scheduled for delivery on 10/20/22. Caulk delivered by SJH on 10/14. EZ.21 truck delivery is still en route, no tracking is available and they can't give us any more information on the driver's progress. *SJH - 10/19/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse $80K profit - why? missing/miscoded invoices? Extra profit is from bathroom hardware order (not yet placed to save space in shop - pricing held on quote from HD Supply) *SJH - 10/19/22 | Jason B. & Kyle M. Say that the job is likely to CLOSE in October, with work beginning in November. Still no confirmation on start date from KMW - *SJH - 10/19/22
St. Marks | SJH |  |  |  | CO for storage fees approved and charged. Still no definite date on completion of breezeway gypcrete, but Caleb says the building should be ready for us "in two weeks". They have asked us to install gutters on #5 & Pool house ASAP - Rigo might be able to go as early as 10/20/22. *SJH - 10/19/22 | Potential future job - vinyl ceilings in breezeways. Nothing new as of 9/2/22. No decision has been made here yet. *Caleb still doesn't have answer on this - it is not likely that this will be awarded at this point since the property is selling in a few weeks. *SJH - 10/19/22
HRP Waterway |  | Samir |  |  | First 5 Truckloads have been delivered, Next 9 Trucks should arrive on or before 11/29. Also Ordered Breezeway Solid Soffit from Alside. *OCN 10/19/22. Need subcontract agreements - Samir - Hardie picking up 320 of 5/4x12 *OCN 11/10/22 | Need subcontract for Samir*
Carlisle Reno |  |  |  |  | Job is completed and invoice was sent a month ago. Waiting on payment to be made. *SJH - 10/19/22
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Manuel making corrections to framing repairs, reinstalling jack posts as permanent fixtures with (3) 2x8 beam, installing drywall and getting ready for final inspections. At current pace, Manuel should finish with work on 10/20 or 10/21. Final inspections to be performed at beginning of following week based on inspectors availability. *SJH - 10/19/22 | Sam working with engineer to get pricing together for recently damaged exterior wall. Engineer is to submit repair plan for review on 10/19/22. *SJH - 10/19/22
Springbranch - Becon (Wilmington, NC) | Wes | Rogelio/Rigo |  |  | Replace 60 sashes | Waiting for confirmation for materials to arrive.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (4/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Melanie Combs house
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Get pricing together to complete panel replacement. *SJH - 10/19/22
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ariston Place - Windsor |  |  |  |  | Awaiting Subcontract *OCN 10/26/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | All currently awarded work has been completed. Property is working through budgets to approve outstanding quotes.
SC Hail Job

## 12.2.22
Team Meeting
12.2.22
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | File Naming Strategies - use descriptive words like "Plans" as this makes it easier to locate later on
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | Sub calendar
4.) | Daily JOB sheets must be filled out. They will cover our ass eventually due to the sorry ass superintendents we are dealing with on 90% of our jobs. Follow up with emails and/or text messages.
5.) | Prelim Job Checklist - PO - enter prior to job start - Contract (new log - in this workbook)
6.) | Vehicle Inspections 1998 GMC, 2007 Chevy, Service Truck
7.) | Time to tidy up office - Trash days Tuesday and Friday - if trash hasn't been taken out to curb when you are leaving the night before or arriving , please take it out.
8.) | Hotels - ask your subs to send you receipts so you can check to be sure we aren't over charged. Put receipts in their CC folder with your initials and date on it so we know it's been reviewed.
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Manuel installed handrails on bldg 2 breezeways on 10/17. Waiting on bldgs 1 & 3 to be ready to install breezeway siding and soffit. *SJH - 10/19/22 |  | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Remaining metal roofing order delivered on Tuesday, 8/30/22. Roofers began installing shingles on bldg 4 and metal on all bldgs. Zavala's measurements and quantities were incorrect - please see action items to the right. *SJH 9/6/22 | Supplementary metal to be picked up between 9/8-9/9. Wes/CJ to take it if it arrives on 9/8, SJH to take it if it arrives on 9/9. *SJH 9/8/22
KMW Church St Lofts (4/2022) | SJH |  |  |  | TKG working on installing corridor base and handrails backing, exterior and storage doors throughout the rest of the building, and hardware kits for units that are ready. *SJH - 10/19/22 | Stay up to date on drywall progress.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Cipriano working on courtyard of #2 until the weekend of 10/21, then he's moving to the outside of the building while grading and pool are installed. Hardie truck #11 scheduled for delivery on 10/20/22. Caulk delivered by SJH on 10/14. EZ.21 truck delivery is still en route, no tracking is available and they can't give us any more information on the driver's progress. *SJH - 10/19/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse $80K profit - why? missing/miscoded invoices? Extra profit is from bathroom hardware order (not yet placed to save space in shop - pricing held on quote from HD Supply) *SJH - 10/19/22 | Jason B. & Kyle M. Say that the job is likely to CLOSE in October, with work beginning in November. Still no confirmation on start date from KMW - *SJH - 10/19/22
St. Marks | SJH |  |  |  | CO for storage fees approved and charged. Still no definite date on completion of breezeway gypcrete, but Caleb says the building should be ready for us "in two weeks". They have asked us to install gutters on #5 & Pool house ASAP - Rigo might be able to go as early as 10/20/22. *SJH - 10/19/22 | Potential future job - vinyl ceilings in breezeways. Nothing new as of 9/2/22. No decision has been made here yet. *Caleb still doesn't have answer on this - it is not likely that this will be awarded at this point since the property is selling in a few weeks. *SJH - 10/19/22
HRP Waterway |  | Samir |  |  | First 5 Truckloads have been delivered, Next 9 Trucks should arrive on or before 11/29. Also Ordered Breezeway Solid Soffit from Alside. *OCN 10/19/22. Need subcontract agreements - Samir - Hardie picking up 320 of 5/4x12 *OCN 11/10/22 | Need subcontract for Samir*
Carlisle Reno |  |  |  |  | Job is completed and invoice was sent a month ago. Waiting on payment to be made. *SJH - 10/19/22
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Manuel making corrections to framing repairs, reinstalling jack posts as permanent fixtures with (3) 2x8 beam, installing drywall and getting ready for final inspections. At current pace, Manuel should finish with work on 10/20 or 10/21. Final inspections to be performed at beginning of following week based on inspectors availability. *SJH - 10/19/22 | Sam working with engineer to get pricing together for recently damaged exterior wall. Engineer is to submit repair plan for review on 10/19/22. *SJH - 10/19/22
Springbranch - Becon (Wilmington, NC) | Wes | Rogelio/Rigo |  |  | Replace 60 sashes | Waiting for confirmation for materials to arrive.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (4/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Melanie Combs house
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Get pricing together to complete panel replacement. *SJH - 10/19/22
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ariston Place - Windsor |  |  |  |  | Awaiting Subcontract *OCN 10/26/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | All currently awarded work has been completed. Property is working through budgets to approve outstanding quotes.
SC Hail Job

## 11.10.22
Team Meeting
11.10.22
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | File Naming Strategies - use descriptive words like "Plans" as this makes it easier to locate later on
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | Sub calendar
4.) | Daily JOB sheets must be filled out. They will cover our ass eventually due to the sorry ass superintendents we are dealing with on 90% of our jobs. Follow up with emails and/or text messages.
5.) | Prelim Job Checklist - PO - enter prior to job start - Contract (new log - in this workbook)
6.) | Vehicle Inspections 1998 GMC, 2007 Chevy, Service Truck
7.) | Time to tidy up office - Trash days Tuesday and Friday - if trash hasn't been taken out to curb when you are leaving the night before or arriving , please take it out.
8.) | Hotels - ask your subs to send you receipts so you can check to be sure we aren't over charged. Put receipts in their CC folder with your initials and date on it so we know it's been reviewed.
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Manuel installed handrails on bldg 2 breezeways on 10/17. Waiting on bldgs 1 & 3 to be ready to install breezeway siding and soffit. *SJH - 10/19/22 |  | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Remaining metal roofing order delivered on Tuesday, 8/30/22. Roofers began installing shingles on bldg 4 and metal on all bldgs. Zavala's measurements and quantities were incorrect - please see action items to the right. *SJH 9/6/22 | Supplementary metal to be picked up between 9/8-9/9. Wes/CJ to take it if it arrives on 9/8, SJH to take it if it arrives on 9/9. *SJH 9/8/22
KMW Church St Lofts (4/2022) | SJH |  |  |  | TKG working on installing corridor base and handrails backing, exterior and storage doors throughout the rest of the building, and hardware kits for units that are ready. *SJH - 10/19/22 | Stay up to date on drywall progress.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Cipriano working on courtyard of #2 until the weekend of 10/21, then he's moving to the outside of the building while grading and pool are installed. Hardie truck #11 scheduled for delivery on 10/20/22. Caulk delivered by SJH on 10/14. EZ.21 truck delivery is still en route, no tracking is available and they can't give us any more information on the driver's progress. *SJH - 10/19/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse $80K profit - why? missing/miscoded invoices? Extra profit is from bathroom hardware order (not yet placed to save space in shop - pricing held on quote from HD Supply) *SJH - 10/19/22 | Jason B. & Kyle M. Say that the job is likely to CLOSE in October, with work beginning in November. Still no confirmation on start date from KMW - *SJH - 10/19/22
St. Marks | SJH |  |  |  | CO for storage fees approved and charged. Still no definite date on completion of breezeway gypcrete, but Caleb says the building should be ready for us "in two weeks". They have asked us to install gutters on #5 & Pool house ASAP - Rigo might be able to go as early as 10/20/22. *SJH - 10/19/22 | Potential future job - vinyl ceilings in breezeways. Nothing new as of 9/2/22. No decision has been made here yet. *Caleb still doesn't have answer on this - it is not likely that this will be awarded at this point since the property is selling in a few weeks. *SJH - 10/19/22
HRP Waterway |  | Samir |  |  | First 5 Truckloads have been delivered, Next 9 Trucks should arrive on or before 11/29. Also Ordered Breezeway Solid Soffit from Alside. *OCN 10/19/22. Need subcontract agreements - Samir - Hardie picking up 320 of 5/4x12 *OCN 11/10/22 | Need subcontract for Samir*
Carlisle Reno |  |  |  |  | Job is completed and invoice was sent a month ago. Waiting on payment to be made. *SJH - 10/19/22
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Manuel making corrections to framing repairs, reinstalling jack posts as permanent fixtures with (3) 2x8 beam, installing drywall and getting ready for final inspections. At current pace, Manuel should finish with work on 10/20 or 10/21. Final inspections to be performed at beginning of following week based on inspectors availability. *SJH - 10/19/22 | Sam working with engineer to get pricing together for recently damaged exterior wall. Engineer is to submit repair plan for review on 10/19/22. *SJH - 10/19/22
Springbranch - Becon (Wilmington, NC) | Wes | Rogelio/Rigo |  |  | Replace 60 sashes | Waiting for confirmation for materials to arrive.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (4/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Melanie Combs house
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Get pricing together to complete panel replacement. *SJH - 10/19/22
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Fairway PH2 |  |  |  |  | Bid sent to C. Binkowski on 11-10-22 *OCN 11/10/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ariston Place - Windsor |  |  |  |  | Awaiting Subcontract *OCN 10/26/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | All currently awarded work has been completed. Property is working through budgets to approve outstanding quotes.
SC Hail Job

## 10.27.22
Team Meeting
2022-10-27
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | File Naming Strategies - use descriptive words like "Plans" as this makes it easier to locate later on
2.) | Siding/roofing/gutter/door/window pricing template (Do we have this? Timeline of initiative?) Nov 15 target date **Uplouded to SharePoint 10/28/22 *OCN**
3.) | Sub calendar
4.) | Daily JOB sheets must be filled out. They will cover our ass eventually due to the sorry ass superintendents we are dealing with on 90% of our jobs. Follow up with emails and/or text messages.
5.) | Prelim Job Checklist - PO - enter prior to job start - Contract (new log - in this workbook)
6.) | Vehicle Inspections 1998 GMC, 2007 Chevy, Service Truck
7.) | Time to tidy up office - Trash days Tuesday and Friday - if trash hasn't been taken out to curb when you are leaving the night before or arriving , please take it out.
8.) | Hotels - ask your subs to send you receipts so you can check to be sure we aren't over charged. Put receipts in their CC folder with your initials and date on it so we know it's been reviewed.
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Manuel installed handrails on bldg 2 breezeways on 10/17. Waiting on bldgs 1 & 3 to be ready to install breezeway siding and soffit. *SJH - 10/19/22 |  | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Remaining metal roofing order delivered on Tuesday, 8/30/22. Roofers began installing shingles on bldg 4 and metal on all bldgs. Zavala's measurements and quantities were incorrect - please see action items to the right. *SJH 9/6/22 | Supplementary metal to be picked up between 9/8-9/9. Wes/CJ to take it if it arrives on 9/8, SJH to take it if it arrives on 9/9. *SJH 9/8/22
KMW Church St Lofts (4/2022) | SJH |  |  |  | TKG working on installing corridor base and handrails backing, exterior and storage doors throughout the rest of the building, and hardware kits for units that are ready. *SJH - 10/19/22 | Stay up to date on drywall progress.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Cipriano working on courtyard of #2 until the weekend of 10/21, then he's moving to the outside of the building while grading and pool are installed. Hardie truck #11 scheduled for delivery on 10/20/22. Caulk delivered by SJH on 10/14. EZ.21 truck delivery is still en route, no tracking is available and they can't give us any more information on the driver's progress. *SJH - 10/19/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse $80K profit - why? missing/miscoded invoices? Extra profit is from bathroom hardware order (not yet placed to save space in shop - pricing held on quote from HD Supply) *SJH - 10/19/22 | Jason B. & Kyle M. Say that the job is likely to CLOSE in October, with work beginning in November. Still no confirmation on start date from KMW - *SJH - 10/19/22
St. Marks | SJH |  |  |  | CO for storage fees approved and charged. Still no definite date on completion of breezeway gypcrete, but Caleb says the building should be ready for us "in two weeks". They have asked us to install gutters on #5 & Pool house ASAP - Rigo might be able to go as early as 10/20/22. *SJH - 10/19/22 | Potential future job - vinyl ceilings in breezeways. Nothing new as of 9/2/22. No decision has been made here yet. *Caleb still doesn't have answer on this - it is not likely that this will be awarded at this point since the property is selling in a few weeks. *SJH - 10/19/22
HRP Waterway |  |  |  |  | First 5 Truckloads have been delivered, Next 9 Trucks should arrive on or before 11/29. Also Ordered Breezeway Solid Soffit from Alside. *OCN 10/19/22. Need subcontract agreements - Samir
Carlisle Reno |  |  |  |  | Job is completed and invoice was sent a month ago. Waiting on payment to be made. *SJH - 10/19/22
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Manuel making corrections to framing repairs, reinstalling jack posts as permanent fixtures with (3) 2x8 beam, installing drywall and getting ready for final inspections. At current pace, Manuel should finish with work on 10/20 or 10/21. Final inspections to be performed at beginning of following week based on inspectors availability. *SJH - 10/19/22 | Sam working with engineer to get pricing together for recently damaged exterior wall. Engineer is to submit repair plan for review on 10/19/22. *SJH - 10/19/22
Springbranch - Becon (Wilmington, NC) | Wes | Rogelio/Rigo |  |  | Replace 60 sashes | Waiting for confirmation for materials to arrive.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (4/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Melanie Combs house
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Get pricing together to complete panel replacement. *SJH - 10/19/22
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
WC - Pegram Landing Ph2 |  |  |  |  | Updated quote sent 11/1/22 *OCN
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Estimate sent *OCN 10/18/22
Ariston Place - Windsor |  |  |  |  | Awaiting Subcontract *OCN 10/26/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | All currently awarded work has been completed. Property is working through budgets to approve outstanding quotes.
SC Hail Job

## 10.19.22
Team Meeting
2022-10-19
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | Siding/roofing/gutter/door/window pricing template
3.) | Sub calendar
4.) | Daily JOB sheets must be filled out. They will cover our ass eventually due to the sorry ass superintendents we are dealing with on 90% of our jobs. Follow up with emails and/or text messages.
5.) | Job names on invoices - need your help - text job names to subs and ask them to reference them on their invoices rather than "Asheboro or Myrtle Beach"
6.) | Vehicle Inspections 1998 GMC, 2007 Chevy, Service Truck
7.) | Time to tidy up office - Trash days Tuesday and Friday - if trash hasn't been taken out to curb when you are leaving the night before or arriving , please take it out.
8.) | Hotels - ask your subs to send you receipts so you can check to be sure we aren't over charged. Put receipts in their CC folder with your initials and date on it so we know it's been reviewed.
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Manuel installed handrails on bldg 2 breezeways on 10/17. Waiting on bldgs 1 & 3 to be ready to install breezeway siding and soffit. *SJH - 10/19/22 |  | 2022-08-25
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Remaining metal roofing order delivered on Tuesday, 8/30/22. Roofers began installing shingles on bldg 4 and metal on all bldgs. Zavala's measurements and quantities were incorrect - please see action items to the right. *SJH 9/6/22 | Supplementary metal to be picked up between 9/8-9/9. Wes/CJ to take it if it arrives on 9/8, SJH to take it if it arrives on 9/9. *SJH 9/8/22
KMW Church St Lofts (4/2022) | SJH |  |  |  | TKG working on installing corridor base and handrails backing, exterior and storage doors throughout the rest of the building, and hardware kits for units that are ready. *SJH - 10/19/22 | Stay up to date on drywall progress.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Cipriano working on courtyard of #2 until the weekend of 10/21, then he's moving to the outside of the building while grading and pool are installed. Hardie truck #11 scheduled for delivery on 10/20/22. Caulk delivered by SJH on 10/14. EZ.21 truck delivery is still en route, no tracking is available and they can't give us any more information on the driver's progress. *SJH - 10/19/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse $80K profit - why? missing/miscoded invoices? Extra profit is from bathroom hardware order (not yet placed to save space in shop - pricing held on quote from HD Supply) *SJH - 10/19/22 | Jason B. & Kyle M. Say that the job is likely to CLOSE in October, with work beginning in November. Still no confirmation on start date from KMW - *SJH - 10/19/22
St. Marks | SJH |  |  |  | CO for storage fees approved and charged. Still no definite date on completion of breezeway gypcrete, but Caleb says the building should be ready for us "in two weeks". They have asked us to install gutters on #5 & Pool house ASAP - Rigo might be able to go as early as 10/20/22. *SJH - 10/19/22 | Potential future job - vinyl ceilings in breezeways. Nothing new as of 9/2/22. No decision has been made here yet. *Caleb still doesn't have answer on this - it is not likely that this will be awarded at this point since the property is selling in a few weeks. *SJH - 10/19/22
HRP Waterway |  |  |  |  | First Truck delivery 10/13/22, All Siding Trucks have been ordered. Also Ordered Breezeway Solid Soffit from Alside. *OCN 10/19/22. Need subcontract agreements - Abel
Carlisle Reno |  |  |  |  | Job is completed and invoice was sent a month ago. Waiting on payment to be made. *SJH - 10/19/22
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Manuel making corrections to framing repairs, reinstalling jack posts as permanent fixtures with (3) 2x8 beam, installing drywall and getting ready for final inspections. At current pace, Manuel should finish with work on 10/20 or 10/21. Final inspections to be performed at beginning of following week based on inspectors availability. *SJH - 10/19/22 | Sam working with engineer to get pricing together for recently damaged exterior wall. Engineer is to submit repair plan for review on 10/19/22. *SJH - 10/19/22
Springbranch - Becon (Wilmington, NC) | Wes | Rogelio/Rigo |  |  | Replace 60 sashes | Waiting for confirmation for materials to arrive.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (4/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Melanie Combs house
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Get pricing together to complete panel replacement. *SJH - 10/19/22
PPM - Regal Oaks |  |  |  | Jason Buffkin | Need to send Jason pricing for structural repairs ASAP. *SJH - 10/19/22
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Put off until 2023 | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | EZ Trim Quote from Southern Carlson recieved 9-7-22 Need to send revised Estimate *OCN 9/8/22
Ariston Place - Windsor |  |  |  |  | Bid was sent
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | All currently awarded work has been completed. Property is working through budgets to approve outstanding quotes.
SC Hail Job

## 9.12.22
Team Meeting
2022-09-08
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | Siding/roofing/gutter/door/window pricing template
3.) | Sub calendar
4.) | Daily JOB sheets must be filled out. They will cover our ass eventually due to the sorry ass superintendents we are dealing with on 90% of our jobs. Follow up with emails and/or text messages.
5.) | Job names on invoices - need your help - text job names to subs and ask them to reference them on their invoices rather than "Asheboro or Myrtle Beach"
6.) | Vehicle Inspections 1998 GMC, 2007 Chevy, Service Truck
7.) | Time to tidy up office - Trash days Tuesday and Friday - if trash hasn't been taken out to curb when you are leaving the night before or arriving , please take it out.
8.) | Hotels - ask your subs to send you receipts so you can check to be sure we aren't over charged. Put receipts in their CC folder with your initials and date on it so we know it's been reviewed.
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Rigo working on bldg 2 & 3 gutters. Manuel beginning breezeway siding and soffit installation. *SJH 9/6/22 Manuel to finish first 2 floors of bldg 2 by CoB Friday, 9/9/22. *SJH 9/8/22 | Sam Delivered Heather J Channel (10 boxes) & trim coil (15 rolls) on Wednesday, 9/7/22. | 2022-08-25
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Remaining metal roofing order delivered on Tuesday, 8/30/22. Roofers began installing shingles on bldg 4 and metal on all bldgs. Zavala's measurements and quantities were incorrect - please see action items to the right. *SJH 9/6/22 | Supplementary metal to be picked up between 9/8-9/9. Wes/CJ to take it if it arrives on 9/8, SJH to take it if it arrives on 9/9. *SJH 9/8/22
KMW Church St Lofts (4/2022) | SJH |  |  |  | TKG is on-site installing hardware and remaining trim for first sets of units (after painting). 1st floor area B & C to begin doors and trim on Wednesday, 9/7/22. Manuel completed temporary window framing and new trim CO on Friday, 9/2/22. Drywall and paint crews SUCK! Drywall is way behind and paint is coming in while we're working in units. No Bueno!! *SJH 9/6/22 | Stay up to date on drywall progress.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | First deliveries still show 9/9, but Hardie says it will not likely ship on this date due to not yet having a carrier in place. C. Little to update once material has been picked up by carrier *SJH 9/8/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse $80K profit - why? missing/miscoded invoices? Sam to review job cost. | Jason B. & Kyle M. Say that the job is likely to CLOSE in September, with work beginning in October *SJH 7/19/22
St. Marks | SJH |  |  |  | Brick is finally complete on exterior of bldg. Gypcrete in breezeway to be completed "in ~2 weeks", per Caleb. Property is supposed to sell in October. Manuel worked on siding over the weekend and will return when he finishes in Asheville. *SJH 9/6/22 CO for storage unit 12 months - Sam to complete | Potential future job - vinyl ceilings in breezeways. Nothing new as of 9/2/22. No decision has been made here yet.
HRP Waterway |  |  |  |  | First Truck delivery on or before 10/4/22 *OCN 9/8/22 Need subcontract agreements - Abel
Carlisle Reno |  |  |  |  | Still trying to get return correspondence from the fire Marshall's office for the inspection. Larry Howard (GFD) finally returned call on Thursday evening, 9/1/22 and gave another phone contact. Called twice on Friday 9/2 and once on Tuesday 9/6, left messages both times. Informed Craig and asked for assistance in reaching out to the inspector. *SJH 9/6/22. | GFD called back on 9/6/22 @ 12:20pm - we are on schedule for fire inspection on 9/14/22 @ 3:30pm. They will try to get someone out sooner if possible - C. Roberson has been informed of status in-full. *SJH 9/6/22
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Permit finally approved and paid for on 9/6/22. SJH to visit Larchmont to go over repairs with Rigo prior to calling for engineer's inspection. *SJH 9/6/22.
Springbranch (Wilmington, NC) | Wes | Rogelio/Rigo |  |  | Replace 60 sashes | Waiting for confirmation for materials to arrive.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (2/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Melanie Combs house
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Estimate to replace additional panels at stairs submitted to Jason on Monday, 7/18/22. Plan to complete this work while crew is at Larchmont, pending property approval. Jason is seeking approval from owner for this change order. *SJH 7/28/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Need to visit to measure for doors, windows, hardware, roofing, etc. Check on takeoffs and estimate to see what the job involves. *SJH 8/24/22. | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | EZ Trim Quote from Southern Carlson recieved 9-7-22 Need to send revised Estimate *OCN 9/8/22
Ariston Place - Windsor |  |  |  |  | Bid was sent
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Scheduled Carlos to make brick repairs asap - waiting on his ETA for materials (property has been notified). Keith & Sam to visit property on 8/24/22 to complete grading estimate. *SJH 8/24/22
SC Hail Job

## 9.8.22
Team Meeting
2022-09-08
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | Siding/roofing/gutter/door/window pricing template
3.) | Sub calendar
4.) | Daily JOB sheets must be filled out. They will cover our ass eventually due to the sorry ass superintendents we are dealing with on 90% of our jobs. Follow up with emails and/or text messages.
5.) | Job names on invoices - need your help - text job names to subs and ask them to reference them on their invoices rather than "Asheboro or Myrtle Beach"
6.) | Vehicle Inspections 1998 GMC
7.) | Time to tidy up office
8.) | Hotels
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Rigo working on bldg 2 & 3 gutters. Manuel beginning breezeway siding and soffit installation. *SJH 9/6/22 Manuel to finish first 2 floors of bldg 2 by CoB Friday, 9/9/22. *SJH 9/8/22 | Sam Delivered Heather J Channel (10 boxes) & trim coil (15 rolls) on Wednesday, 9/7/22. | 2022-08-25
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Remaining metal roofing order delivered on Tuesday, 8/30/22. Roofers began installing shingles on bldg 4 and metal on all bldgs. Zavala's measurements and quantities were incorrect - please see action items to the right. *SJH 9/6/22 | Supplementary metal to be picked up between 9/8-9/9. Wes/CJ to take it if it arrives on 9/8, SJH to take it if it arrives on 9/9. *SJH 9/8/22
KMW Church St Lofts (4/2022) | SJH |  |  |  | TKG is on-site installing hardware and remaining trim for first sets of units (after painting). 1st floor area B & C to begin doors and trim on Wednesday, 9/7/22. Manuel completed temporary window framing and new trim CO on Friday, 9/2/22. Drywall and paint crews SUCK! Drywall is way behind and paint is coming in while we're working in units. No Bueno!! *SJH 9/6/22 | Stay up to date on drywall progress.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | First deliveries still show 9/9, but Hardie says it will not likely ship on this date due to not yet having a carrier in place. C. Little to update once material has been picked up by carrier *SJH 9/8/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse $80K profit - why? missing/miscoded invoices? Sam to review job cost. | Jason B. & Kyle M. Say that the job is likely to CLOSE in September, with work beginning in October *SJH 7/19/22
St. Marks | SJH |  |  |  | Brick is finally complete on exterior of bldg. Gypcrete in breezeway to be completed "in ~2 weeks", per Caleb. Property is supposed to sell in October. Manuel worked on siding over the weekend and will return when he finishes in Asheville. *SJH 9/6/22 CO for storage unit 12 months - Sam to complete | Potential future job - vinyl ceilings in breezeways. Nothing new as of 9/2/22. No decision has been made here yet.
HRP Waterway |  |  |  |  | First Truck delivery on or before 10/4/22 *OCN 9/8/22 Need subcontract agreements - Abel
Carlisle Reno |  |  |  |  | Still trying to get return correspondence from the fire Marshall's office for the inspection. Larry Howard (GFD) finally returned call on Thursday evening, 9/1/22 and gave another phone contact. Called twice on Friday 9/2 and once on Tuesday 9/6, left messages both times. Informed Craig and asked for assistance in reaching out to the inspector. *SJH 9/6/22. | GFD called back on 9/6/22 @ 12:20pm - we are on schedule for fire inspection on 9/14/22 @ 3:30pm. They will try to get someone out sooner if possible - C. Roberson has been informed of status in-full. *SJH 9/6/22
PPM - Larchmont (Asheville, NC) | SJH | Rigo |  | Jason Buffkin | Permit finally approved and paid for on 9/6/22. SJH to visit Larchmont to go over repairs with Rigo prior to calling for engineer's inspection. *SJH 9/6/22.
Springbranch (Wilmington, NC) | Wes | Rogelio/Rigo |  |  | Replace 60 sashes | Waiting for confirmation for materials to arrive.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (2/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Melanie Combs house
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Estimate to replace additional panels at stairs submitted to Jason on Monday, 7/18/22. Plan to complete this work while crew is at Larchmont, pending property approval. Jason is seeking approval from owner for this change order. *SJH 7/28/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen - Brevard | Not KW |  | 2022-08-22 | KMW | Need to visit to measure for doors, windows, hardware, roofing, etc. Check on takeoffs and estimate to see what the job involves. *SJH 8/24/22. | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | EZ Trim Quote from Southern Carlson recieved 9-7-22 Need to send revised Estimate *OCN 9/8/22
Ariston Place - Windsor |  |  |  |  | Bid was sent
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Scheduled Carlos to make brick repairs asap - waiting on his ETA for materials (property has been notified). Keith & Sam to visit property on 8/24/22 to complete grading estimate. *SJH 8/24/22
SC Hail Job

## 8.24.22
Team Meeting
2022-08-24
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | Siding/roofing/gutter/door/window pricing template
3.) | Sub calendar - *SJH updated for week of 8/15-8/19
4.) | Daily JOB sheets must be filled out. They will cover our ass eventually due to the sorry ass superintendents we are dealing with on 90% of our jobs. Follow up with emails and/or text messages.
5.) | Hillstone work at Wesco jobs - billing - ideas to streamline process and keep communication with Wesco without "surprise work"
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Building 2 Breezeways are ready for siding | Manuel installing vinyl on buidling 2 | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Building 1300 concrete poured 8-23. Was supposed to be poured first week of august. Was told on 8-19 by CSM and TC that 1300 was ready. Sent crew on Monday and it was not ready. See 8-23 job report for more info. 1500 concrete to be poured 9-8? |  | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Building 1,2 and 5 metal roofs delivered. Framers suck and are not doing what they say they will do. Roof on garage and building 4 will should be ready monday 8-29. Again framers suck. See daily job report for 8-22. | Metal roofing for last 2 buildings ordered on Monday, 8/22. Waiting on ETA from Triad. *SJH 8/24/22 |  | Zavala contract executed - Abels needs to be turned in.
KMW Church St Lofts (4/2022) | SJH |  |  |  | Began door & trim installation on 1st floor "area A" on Monday, 8/22/24. Drywall crew is fucking us... again. TKG & Manuel are there as of 8/24/22 and the last 5 units still haven't been sanded (sanding began on 8/19 & 8/22, but still isn't completed). Moving forward at our normal pace to maintain our timeline. *SJH 8/24/22
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | C. Little says that Hardie is asking to stagger deliveries - Hardie wants (1) truck/week, but we have requested (2) trucks/week. *SJH 8/24/22 | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Guys not onsite this week due to wtf? 2 weeks to finish columns. waiting on abel for confirmation. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Jason B. & Kyle M. Say that the job is likely to CLOSE in September, with work beginning in October *SJH 7/19/22
St. Marks | SJH |  |  |  | Manuel began installing siding on Thursday, 8/11/22. He was pulled off on 8/15 to handle CO for KMW, but will back on-site around Wednesday, 8/17/22. Brick is complete and Manuel is ~25% complete with the exterior siding. Plans for dumpster gates sent to WA & KB for review - they want a price to build and install. *SJH 8/15/22.
HRP Waterway |  |  |  |  | Sent 5 truck load PO's to Lansing *OCN 8/4/22
Carlisle Reno |  |  |  |  | Waiting on Fire Marshall to complete fire inspection so that final building inspection can be passed. SJH has reached out to the fire marshall every day since 8/19/22 and has left messages - sent email to his address on Monday & Tuesday, 8/22-23/22. Will continue to follow up throughout week until fire marshall is scheduled. *SJH 8/24/22
PPM - Larchmont | SJH | Rigo |  | Jason Buffkin | Rigo should complete work week of 8/22-26. Drywall repairs to begin on Wednesday, 8/24/22. Jason is visiting the job site on 8/24/22. *SJH 8/24/22
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Brightwood (4/2023)
Wakefield (2/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22 | SJH to follow up with Lansing on duration of pricing hold, as well as with KMW for job progress. Materials need to be ordered before contract pricing increases, but need to hold out as long as possible due to delayed job-start date. *SJH 8/24/22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Estimate to replace additional panels at stairs submitted to Jason on Monday, 7/18/22. Plan to complete this work while crew is at Larchmont, pending property approval. Jason is seeking approval from owner for this change order. *SJH 7/28/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Need to visit to measure for doors, windows, hardware, roofing, etc. Check on takeoffs and estimate to see what the job involves. *SJH 8/24/22. | Go measure week of 8/29-9/2/22
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HKJ Magnolia Hills
HKJ Broadstone |  |  |  |  | Bid has been sent
HKJ Wynslow |  |  |  |  | Bid has been sent
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | We received the EZ Trim quote, need to review with Wes, then send to Southern Carlson for pricing *OCN 8/24/22
Ariston Place - Windsor |  |  |  |  | Bid was sent
Ginkgo - Glendare |  |  |  | Paul Sidam | Received return correspondence from Ginkgo that they are reviewing our price, but said that on first glance it is significantly higher. *SJH 8/24/22
Ashley Oaks - Living Well Homes |  |  |  |  | Scheduled Carlos to make brick repairs asap - waiting on his ETA for materials (property has been notified). Keith & Sam to visit property on 8/24/22 to complete grading estimate. *SJH 8/24/22

## 8.15.22
Team Meeting
2022-08-15
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | Siding/roofing/gutter/door/window pricing template
3.) | Sub calendar - *SJH updated for week of 8/15-8/19
4.) | Vehicle inspections
5.) | Hillstone work at Wesco jobs - billing - ideas to streamline process and keep communication with Wesco without "surprise work"
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | CONTRACTS
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Cipriano pulled off becasue nothing is ready for us. Keith installing rails on building 1 | Vinyl siding is ready for install on building 2 | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Will be finished with exteriors by 7/25/22. Breezeway being poured first week of August. | Gutters/downspouts on 1500 and downspouts on 1300 | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Still waiting on roof inspections. Metal Roofing order for first three buildings was placed on Friday, 8/12/22. *SJH 8/15/22 | Send PO to Superior for delivery tomorrow |  | Zavala contract executed - Abels needs to be turned in.
KMW Church St Lofts (4/2022) | SJH |  |  |  | Completed door and baseboard installation for 2nd floor "area A" on Thursday, 8/11/22. Returning on Tuesday, 8/16 to install cut-glass window trim and baseboards in units that have now received cabinets. Door installation in 1st floor "area A" to begin on Wednesday, 8/17/22. Manuel is on-site covering openings with plastic. First CO sent to K. McDowell on 8/15 - second CO to follow for full-framing of plastic covered windows. Materials on white trailer to be delivered to job-site on 8/16/22 *SJH 8/15/22.
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Hardie trucks 1-4 delivery on 9/9/22. Hardie trucks 5-10 delivery on 9/14/22. Remaining trucks to be ordered 1-2 wekks after installation begins to ensure material counts are accurate for installation method. SJH 7/28/22. | Tiger wood planks sourced through Beeson Hardware, per Scott Boswell. Order not yet placed, but distributor has confirmed availability. *SJH 8/15/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Should complete outside of building this week. Should be completely finished by end of August. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Jason B. & Kyle M. Say that the job is likely to CLOSE in September, with work beginning in October *SJH 7/19/22
St. Marks | SJH |  |  |  | Manuel began installing siding on Thursday, 8/11/22. He was pulled off on 8/15 to handle CO for KMW, but will back on-site around Wednesday, 8/17/22. Brick is complete and Manuel is ~25% complete with the exterior siding. Plans for dumpster gates sent to WA & KB for review - they want a price to build and install. *SJH 8/15/22.
HRP Waterway |  |  |  |  | Sent 5 truck load PO's to Lansing *OCN 8/4/22
Carlisle Reno |  |  |  |  | Rogelio completed window replacement and final touch-ups on Monday, 8/15/22. Final inspection called in for Tuesday, 8/16/22. *SJH 8/15/22.
PPM - Larchmont | SJH | Rigo |  | Jason Buffkin | Jack post installation and floor jacking in unfinished area completed as of 8/12/22. Rigo will return on Thursday, 8/18 to install gussets in affected area. *SJH 8/15/22.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
PPM - Wind Ridge |  |  |  | Jason Buffkin | Estimate to replace additional panels at stairs submitted to Jason on Monday, 7/18/22. Plan to complete this work while crew is at Larchmont, pending property approval. Jason is seeking approval from owner for this change order. *SJH 7/28/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HRP Pine Forest Phase II
HKJ Broadstone
HKJ Wynslow
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm |  |  |  |  | Waiting on EZ Trim
Ariston Place - Windsor |  |  |  |  | Sent in for pricing *OCN 8/15/22
Ginkgo - Glendare |  |  |  | Paul Sidam | Estimate for interior renovation (cabinets & counter tops) submitted to Paul on Friday, 8/12/22. Will follow up on Tuesday, 8/16/22 *SJH 8/15/22
Ashley Oaks - Living Well Homes |  |  |  |  | SJH to visit property on Tuesday, 8/16/22 to inspect for potential site-work. They need masonry repairs (retaining wall), gutter repairs, drywall repair, and window & door sealant. T. Melton referred them to us. Call came in on 8/15/22. *SJH 8/15/22.

## 8.4.22
Team Meeting
2022-08-04
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | Siding/roofing/gutter/door/window pricing template
3.) | Sub calendar
4.) | Vehicle inspections
5.) | Black and White
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Cipriano pulled off becasue nothing is ready for us. Keith installing rails on building 1 | Vinyl siding will be ready for installation in a couple of weeks. *WA 8/4/22 | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Will be finished with exteriors by 7/25/22. Breezeway being poured first week of August. | Gutters/downspouts on 1500 and downspouts on 1300 | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Follow up about metal roofing. Still waiting on roof inspections. | Send PO to Superior for delivery tomorrow
KMW Church St Lofts (4/2022) | SJH |  |  |  | First half of doors are in the building as of 8/3/22. TKG began installing on 8/4/22. Manuel to begin on Monday, 8/8/22. Unit hardware to be taken out to job-site by Monday, 8/8/22. *SJH 8/4/22
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Hardie trucks 1-4 delivery on 9/9/22. Hardie trucks 5-10 delivery on 9/14/22. Remaining trucks to be ordered 1-2 wekks after installation begins to ensure material counts are accurate for installation method. SJH 7/28/22. | Get Tiger Wood Planks in motion/ordered. J Cubed Brown wants the dog park to get siding ASAP. Use siding from behind shop. Who and When?? *WA 8/4/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Should complete outside of building this week. Should be completely finished by end of August. | Will need (4) pallets of 4x10 to finish columns. CJ to "make it happen" with other material *WA 8/4/22 | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Jason B. & Kyle M. Say that the job is likely to CLOSE in September, with work beginning in October *SJH 7/19/22
St. Marks | SJH |  |  |  | Brick to be completed by end of day on 8/5/22. Siding to begin installation as soon as our crew is available. *SJH 8/4/22
Edgewater Village (4/22/22) | SJH |  |  |  | Payment received from property week of 7/4-7/8. *SJH 7/11/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | 506-G is completed. *SJH 8/4/22.
HRP Waterway |  |  |  |  | Sent 5 truck load PO's to Lansing *OCN 8/4/22
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Carlisle Reno |  |  |  |  | Passed rough framing and insulation inspections on Monday, 8/1/22. JFS to install brick facade on Friday, 8/5/22. *SJH 8/4/22 | Need Rigo or Rogelio to install drywall and finish interior ASAP. Final inspections to be scheduled after work is completed.
PPM - Larchmont | SJH | Rigo |  | Jason Buffkin | Rigo completed gusset installation in crawl space on Friday, 7/22/22. Waiting on engineer's footing plan to continue working in basement area. Sent email to Jason asking for update on footing plan. *SJH 7/28/22 | Need Engineer's footing plan prior to jacking floor week of 7/25/22
PPM - Wind Ridge |  |  |  | Jason Buffkin | Estimate to replace additional panels at stairs submitted to Jason on Monday, 7/18/22. Plan to complete this work while crew is at Larchmont, pending property approval. Jason is seeking approval from owner for this change order. *SJH 7/28/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22 | Potential start of February/Q1 of 2023
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Sent pricing revision to C. Binkowski on 7/28/22.
HRP Pine Forest Phase II
HKJ Broadstone
HKJ Wynslow
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm

## 7.28.22
Team Meeting
2022-07-28
Present: Wes, Sam, Oscar, Stephanie (who looks very nice today) and The Prince(the fab 5 All HERE)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | Siding/roofing/gutter/door/window pricing template
3.) | Sub calendar
4.) | Vehicle inspections
5.) | Receipts - in order oldest to newest
6.) | No one say Andy's or that GD cookie place for at least 8 weeks
7.) | Room for rent - dog for sale $3,500
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Date Inventory Recorded | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Cipriano pulled off becasue nothing is ready for us. Keith installing rails on building 1 |  | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Will be finished with exteriors by 7/25/22. Breezeway being poured first week of August. | Gutters/downspouts on 1500 and downspouts on 1300 | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Follow up about metal roofing. Still waiting on roof inspections. | Send PO to Superior for delivery tomorrow
KMW Church St Lofts (4/2022) | SJH |  |  |  | Door & Trim installation to begin on 8/1/22. Rogelio and TKG to begin installing doors @ 2 units/day per crew. Manuel to take over for Rogelio when he returns from Mexico on 8/4/22. Hardware has been ordered and is scheduled to begin installation in ~2 weeks. Manuel will assign 2 guys to installing hardware to chase the painter. Paint to begin on Wednesday, 8/3/22. SJH 7/28/22
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Hardie trucks 1-4 delivery on 9/9/22. Hardie trucks 5-10 delivery on 9/14/22. Remaining trucks to be ordered 1-2 wekks after installation begins to ensure material counts are accurate for installation method. SJH 7/28/22.
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Should complete outside of building this week. Should be completely finished by end of August. | Change order for columns Cost PLUs | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Jason B. & Kyle M. Say that the job is likely to CLOSE in September, with work beginning in October *SJH 7/19/22
St. Marks | SJH |  |  |  | Brick is still incomplete. SJH visited the site on Wed, 7/27/22 @ ~3pm - no one was working on the brick during his visit. Reached out to Caleb on 7/28/22 for progress update. Will update once reply is received. *SJH 7/28/22
Edgewater Village (4/22/22) | SJH |  |  |  | Payment received from property week of 7/4-7/8. *SJH 7/11/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | 506-G to complete material installation on 7/28/22. Tile back splash to be grouted on 7/28/22. We will be complete with our part of the renovation by CoB 7/28/22. Invoice to be sent on Friday, 7/29/22. *SJH 7/28/22.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
HRP Waterway |  |  |  |  | We need to verify pricing. Contract showed up in my email 6-2-22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Carlisle Reno |  |  |  |  | Rogelio began repair on 7/27/22. Inspection rescheduled for Friday, 7/29/22. Drywall, paint, and brick will need to be completed week of 8/1-8/5. Management has been updated on progress and timeline. *SJH 7/28/22
PPM - Larchmont | SJH | Rigo |  | Jason Buffkin | Rigo completed gusset installation in crawl space on Friday, 7/22/22. Waiting on engineer's footing plan to continue working in basement area. Sent email to Jason asking for update on footing plan. *SJH 7/28/22 | Need Engineer's footing plan prior to jacking floor week of 7/25/22
PPM - Wind Ridge |  |  |  | Jason Buffkin | Estimate to replace additional panels at stairs submitted to Jason on Monday, 7/18/22. Plan to complete this work while crew is at Larchmont, pending property approval. Jason is seeking approval from owner for this change order. *SJH 7/28/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | SJH to submit revised pricing on 7/28/22. Pricing is ready to send off after final review. *SJH 7/28/22
HRP Pine Forest Phase II
HKJ Broadstone
HKJ Wynslow
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm

## 7.18.22
Team Meeting
2022-07-18
Present: Wes, Sam, Oscar, Stephanie (the fab 5 All HERE)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | Siding/roofing/gutter/door/window pricing template
3.) | Email?
4.)
5.)
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Cipriano working in breezeways | Gutters on building 1 | 2022-08-25 | Zavala contract executed - Villeda need to see if in service truck
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Will be finished with exteriors by 7/25/22. Breezeway being poured first week of August. | Gutters/downspouts on 1500 and downspouts on 1300 | 2022-08-22
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Follow up about metal roofing. Still waiting on roof inspections. WES FUCKED UP REAL BAD! | Send PO to Superior for delivery tomorrow
KMW Church St Lofts (4/2022) | SJH |  |  |  | Rigo installing steel for elevator shaft and repairing LVL's for beams - he will be finished on 7/19/22. Trim to begin on 8/3/22, per R. Belvin. No idea when hardware installation can begin due to concrete grinding and general painting *SJH 7/19/22 | Structural beam repair drawing needs to be clarified for Drexler - see notes on drawing for modifications needed. *SJH 6/20/22
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Hardie trucks 1-10 sent to Lansing for order. Waiting on ETA for deliveries. *SJH 7/19/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Should complete outside of building this week. Should be completely finished by end of July. | Change order for columns Cost PLUs | 2022-08-15
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Jason B. & Kyle M. Say that the job is likely to CLOSE in September, with work beginning in October *SJH 7/19/22
St. Marks | SJH |  |  |  | Brick mason is back on-site this week. Knee walls to be completed by end of week so that siding can begin installation. *SJH 7/19/22
Edgewater Village (4/22/22) | SJH |  |  |  | Payment received from property week of 7/4-7/8. *SJH 7/11/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | 506-G was painted on 7/16/22, GYF/Impact completed flooring on 7/18/22. TKG to begin general installation on Wednesday, 7/20/22. Marble Granite World to install hard surface counters on 7/25/22. *SJH 7/19/22 | Need to source (2) bi-fold doors due to back orders with Chadwell. 18" Vanity base to be delivered by Chadwell on 7/19/22
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff in preparation of job ordering. Job is delayed due to extensive blasting that is not yet complete. *SJH 7/11/22
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
HRP Waterway |  |  |  |  | We need to verify pricing. Contract showed up in my email 6-2-22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Carlisle Reno |  |  |  |  | Talked with Craig about potential start dates on Monday, 7/18/22. Waiting on approval from the property/management before scheduling job-start. *SJH 7/19/22 | Follow up with management no later than Wednesday, 7/20/22 to schedule beginning of job.
PPM - Larchmont | SJH | Rigo |  | Jason Buffkin | Submitted revised estimate to Jason on Monday, 7/18/22. Work to begin on Wednesday, 7/20/22 - starting with gussets in crawl space and subfloor @ maint. entry. Engineer to send suggested footing plan for structural jacks by end of this week. *SJH 7/19/22 | Need Engineer's footing plan prior to jacking floor week of 7/25/22
PPM - Wind Ridge |  |  |  | Jason Buffkin | Estimate to replace additional panels at stairs submitted to Jason on Monday, 7/18/22. Plan to complete this work while crew is at Larchmont, pending property approval. *SJH 7/19/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Revised Estimate sent to C. Binkowski on Wednesday, 6/22/22. *SJH 6/24/22
HRP Pine Forest Phase II
HKJ Broadstone
HKJ Wynslow
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID
Windsor 4th&Elm

## 7.11.22
Team Meeting
2022-07-11
Present: Wes, Sam, Oscar, Stephanie (the fab 5 minus 1 CJ SUCKS)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | I missed y'all!
3.) | Siding/roofing/gutter/door/window pricing template
4.) | Communicate where we are going. No need to make multiple trips in same direction
5.) | Opportunity with HKJ. Bidding plans now.
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Cipriano is starting vinyl in breezeways 7-11. | Change order for ceiling at CLubhouse | 2022-07-31 | Zavala contract executed - Villeda need to see if in service truck
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Rogelio finished rails this week. Hillstone finishing dumpster gates next week. |  | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Will be finished with exteriors by 7/25/22. Breezeway being poured first week of August. |  | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel Start Beg Aug. | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Follow up about metal roofing. Still waiting on roof inspections. WES FUCKED UP REAL BAD! | Send PO to Superior for delivery tomorrow
KMW Church St Lofts (4/2022) | SJH |  |  |  | Rigo installing steel for elevator shaft and repairing LVL's for beams. *SJH 7/11/22 | Structural beam repair drawing needs to be clarified for Drexler - see notes on drawing for modifications needed. *SJH 6/20/22
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Manuel to complete stairway panel installation on 7/11/22. Cipriano to begin job in ~2 weeks. *SJH 7/11/22.
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Should complete outside of building this week. Should be completely finished by end of July. | Change order for columns Cost PLUs | 2022-05-30
KMW Springfield | SJH |  |  |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Jason B. & Kyle M. Say that the job is likely to begin in September. *SJH 6/20/22
St. Marks | SJH |  |  |  | Brick mason has gone around the building ~6'H and is beginning to work his way up. Building should be ready to begin siding by 7/13 or 7/14. *SJH 7/11/22
Edgewater Village (4/22/22) | SJH |  |  |  | Payment received from property week of 7/4-7/8. *SJH 7/11/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | 504-D is complete. Invoice has been sent to property. 506-G was demoed on Thursday, 7/7/22. TKG beginning door, cabinet, and baseboard installations on Monday, 7/11/22. Counter template to be created on Tuesday, 7/12/22. Paint and flooring dates still awaiting confirmation from property. *SJH 7/11/22
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Sent Pricing hold list to C. Little on 7/11/22. Working on final ordering takeoff week of 7/11-7/15. *SJH 7/11/22
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
HRP Waterway |  |  |  |  | We need to verify pricing. Contract showed up in my email 6-2-22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Carslyle Reno |  |  |  |  | Met with Engineer on 6/30. Received report on 7/6. Sent updated estimate to property on Friday, 7/8/22. Sending follow-up email in the afternoon of 7/11/22. *SJH 7/11/22
PPM - Larchmont | SJH | Rigo |  | Jason Buffkin | Taking trip to property on Thursday, 7/14/22 to meet with engineer and discuss jack post placement plan and general repair scope. *SJH 7/11/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Revised Estimate sent to C. Binkowski on Wednesday, 6/22/22. *SJH 6/24/22
HRP Pine Forest Phase II
HKJ Broadstone
HKJ Wynslow
Park @ Aventino |  | SAVALA |  |  |  | WA WORKING ON BID

## 6.23.22
Team Meeting
2022-06-20
Present: Wes, Sam, Oscar, Stephanie (the fab 5 minus 1)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | PO - job name job name heads up - carried job not subcategory
3.) | Siding/roofing/gutter/door/window pricing template
4.) | Communicate where we are going. No need to make multiple trips in same direction
5.) | Opportunity with HKJ. Bidding plans now.
6.)
7.) | Fridge - take home what's yours by Thursday. What's left will be in the trash on Friday
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Cipriano will be finished with the general installation in 2 weeks, then he has 1-2 weeks of punch work |  | 2022-07-31 | Zavala contract executed - Villeda need to see if in service truck
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Rogelio finished rails this week. Hillstone finishing dumpster gates next week. |  | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Where are we with punch list. We need to make our own punch list before Hawthorne. We need to get the dumpster gates measured. | Still waiting on last truck of shake and panel. Abel needs 4/4x6, solid and vented soffit. | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Follow up about metal roofing. Still waiting on roof inspections. | Get shakes to job that are at Wes' house
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Manuel still working at Church Street. Trim installation to begin around 7/25/22. *SJH 6/24/22 | Structural beam repair drawing needs to be clarified for Drexler - see notes on drawing for modifications needed. *SJH 6/20/22
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Rigo installed Color Plus panels on Thursday, 6/15, so that they can choose which colors to use. *SJH 6/20/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Need to figure change order for columns and 5/4x8 trim next to doors/windows on patios. Follow up with lansing about 14" x12' soffit |  | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Jason B. & Kyle M. Say that the job is likely to begin in September. *SJH 6/20/22
St. Marks | SJH |  |  |  | Still waiting on brick to be finished so that we can hang siding on Building 5, finish the poolhouse, and put the last pieces of J channel and siding on #1 *SJH 6/10/22 | SJH to follow up with Fixed Point on progress of brick mason. *SJH 6/20/22
Edgewater Village (4/22/22) | SJH |  |  |  | Finished - awaiting payment from property. *SJH 6/10/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | Unit is 90% complete. Cultured top for master bath was damaged upon opening. Should only need 1 more day to complete unit. Planned to be completed on Monday, 6/27/22. *SJH 6/24/22 | Unit 506-G to begin demolition week of 6/27-7/1. Materials have been ordered and Scope of Work has been sent to TKG with labor payouts confirmed. *SJH 6/24/22
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
HRP Waterway |  |  |  |  | We need to verify pricing. Contract showed up in my email 6-2-22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Carslyle Reno |  |  |  |  | Initial bid submitted on 6/3/22. Josh Rose PE to visit property on 7/14/22 to generate repair plan. Final pricing will be adjusted accordingly after this plan becomes available. Carlisle has been notified of these details in complete as of 6/24/22. *SJH 6/24/22
PPM - Larchmont | SJH | Rigo |  | Jason Buffkin | Estimate submitted to J. Buffkin on Friday, 6/24/22. *SJH 6/24/22
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Revised Estimate sent to C. Binkowski on Wednesday, 6/22/22. *SJH 6/24/22

## 6.16.22
Team Meeting
2022-06-20
Present: Wes, Sam, CJ, Stephanie (the fab 4)
Topics
1.) | Contract Review - Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | File Naming Strategy - Property Name Document Name Date
3.) | Blank docs - do not edit - download then save as file naming strategy
4.) | BCBS 7/1/22
5.) | Vehicle Inspections - please let SA know when complete 2020 Chevy KB9444, 1998 GMC JFN7813, 2017 Chevy FFJ8206 (Also Keith's truck)
6.) | Venting conference room - deadline - July 10th
7.) | Fridge - take home what's yours by Thursday. What's left will be in the trash on Friday
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Cipriano will be finished with the general installation in 1.5-2 weeks, then he has 1-2 weeks of punch work, then Change orders. *SJH 6/20/22 | Need (1) pallet of 5/4x8 for Cipriano. *SJH 6/20/22 | 2022-07-31 | Zavala contract executed - Villeda need to see if in service truck
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Hillstone going to complete dumpster gate and 1st floor rails next week. |  | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Where are we with punch list. We need to make our own punch list before Hawthorne. We need to get the dumpster gates measured. | Still waiting on last truck of shake and panel. Abel needs 4/4x6, solid and vented soffit. | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Follow up about metal roofing. Still waiting on roof inspections. | Get shakes to job that are at Wes' house
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Manuel still working at Church Street. *SJH 6/20/22 | Structural beam repair drawing needs to be clarified for Drexler - see notes on drawing for modifications needed. *SJH 6/20/22
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Rigo installed Color Plus panels on Thursday, 6/15, so that they can choose which colors to use. *SJH 6/20/22
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Need to figure change order for columns and 5/4x8 trim next to doors/windows on patios. Follow up with lansing about 14" x12' soffit |  | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Jason B. & Kyle M. Say that the job is likely to begin in September. *SJH 6/20/22
St. Marks | SJH |  |  |  | Still waiting on brick to be finished so that we can hang siding on Building 5, finish the poolhouse, and put the last pieces of J channel and siding on #1 *SJH 6/10/22 | SJH to follow up with Fixed Point on progress of brick mason. *SJH 6/20/22
Edgewater Village (4/22/22) | SJH |  |  |  | Finished - awaiting payment from property. *SJH 6/10/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | Marble Granite World to install hard surface counters on Tuesday, 6/21/22. TKG to complete renovations on Wed-Thurs, 6/22-6/23. *SJH 6/20/22
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
HRP Waterway |  |  |  |  | We need to verify pricing. Contract showed up in my email 6-2-22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Carslyle Reno
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | TKG to begin installing cabinets, doors, and baseboard on Monday, 6/13/22. Porperty will have the unit painted and flooring installed immediately following. *SJH 6/10/22 | Trailer with materials needs to be delivered to CC on Monday morning, 6/13/22.
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Waterway |  |  |  |  | Bid Submitted on 5/12/22. *SJH 5/27/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Initial estimate turned in on 6/20/22. C. Binkowski asked us to add in egress stair rails. *SJH 6/20/22

## 6.9.22
Team Meeting
2022-06-09
Present: Wes, Sam, CJ, Stephanie (the fab 4)
Topics
1.) | Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed) | [6 empty] | WESCO
2.) | Anyone need anything done to their computers? Chris with Zion will be here today.
3.) | PO#/Property Name on phone in orders - if you can put it on your credit card as a monthly auto pay, do that (Example - Mobile Mini, portajohns) | [6 empty] | MEDICAL BENEFITS
4.) | Juneteenth
5.) | [8 empty] | BCBS | BCBS | BCBS | BCBS | BCBS | UHC
6.) | [8 empty] | Current | Renewal | Gold 2000 | Silver 3500 | Silver 4500 | 7000 HSA
7.) | [7 empty] | Deductible | 7000 | 7000 | 2000 | 3500 | 4500 | 7000
PROJECTS | [7 empty] | Total Out Of Pocket | 7000 | 7000 | 6000 | 8700 | 8700 | 7000
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | Primary Office Visit | Ded., 0% | Ded., 0% | $25 copay | $50 copay | $50 copay | Ded., 0%
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Building 1& 2 exteriors are mostly finished. Working on building 3. Chris should have these in Greensboro by close of business today. 6-9-22 | Needs (30) pcs Green (Mountain Sage) 4x10 panel ASAP | 2022-07-31 | Specialist Office Visit | Ded., 0% | Ded., 0% | $50 copay | $100 copay | $100 copay | Ded., 0%
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Hillstone going to complete dumpster gate and 1st floor rails next week. |  | 2022-04-30 | Outpatient Services | Ded., 0% | Ded., 0% | Ded., 20% | Ded., 30% | Ded., 30% | Ded., 0%
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Where are we with punch list. We need to make our own punch list before Hawthorne. We need to get the dumpster gates measured. | Still waiting on last truck of shake and panel. Abel needs 4/4x6, solid and vented soffit. | 2022-06-30 | Inpatient Services | Ded., 0% | Ded., 0% | Ded., 20% | Ded., 30% | Ded., 30% | Ded., 0%
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Follow up about metal roofing. Still waiting on roof inspections. | Get shakes to job that are at Wes' house |  | Emergency Room | Ded., 0% | Ded., 0% | $600 copay | $1000 copay | $1000 copay | Ded., 0%
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Manuel & Rigo were on-site all week framing the chases. They will be there all next week, with Rigo being gone on Monday & Tuesday. *SJH 6/10/22 | Need to get drawing to KMW for structural beam repair. CO sent to KMW for subfloor and beam repair that has already taken place. *SJH 5/20/22 Change orders for bathrrom ceiling removal and reframe, chases. |  | Prescription | Ded., 0% | Ded., 0% | $4/$15/$35/$50/25% | $15/$40/$80/$120/25% | $15/$40/$80/$120/25% | Ded., 0%
KMW Leo Loso/Gateway @ CLT Park $$$ | Wes | Rogelio 4/13 | Cipriano June-August |  | Lansing is bringing in 30 piece of 4x10 for someone to pick colors off of once they are installed on the garage. | Install siding on garages for color selections |  | Lifetime Maximum | Unlimited | Unlimited | Unlimited | Unlimited | Unlimited | Unlimited
KMW Retreat $$$ | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Need to figure change order for columns and 5/4x8 trim next to doors/windows on patios. Follow up with lansing about 14" x12' soffit |  | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Job currently scheduled to begin in July '22, though Kyle McDowell says it could be as late as September '22. *SJH 5/27/22
St. Marks | SJH |  |  |  | Still waiting on brick to be finished so that we can hang siding on Building 5, finish the poolhouse, and put the last pieces of J channel and siding on #1 *SJH 6/10/22
Edgewater Village (4/22/22) | SJH |  |  |  | Finished - awaiting payment from property. *SJH 6/10/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | TKG to begin installing cabinets, doors, and baseboard on Monday, 6/13/22. Porperty will have the unit painted and flooring installed immediately following. *SJH 6/10/22 | Trailer with materials needs to be delivered to CC on Monday morning, 6/13/22.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
Waterway |  |  |  |  | We need to verify pricing. Contract showed up in my email 6-2-22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Carslyle Reno
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | TKG to begin installing cabinets, doors, and baseboard on Monday, 6/13/22. Porperty will have the unit painted and flooring installed immediately following. *SJH 6/10/22 | Trailer with materials needs to be delivered to CC on Monday morning, 6/13/22.
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Waterway |  |  |  |  | Bid Submitted on 5/12/22. *SJH 5/27/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Bid due on 6/21/22 - Takeoffs are 90%+ complete. Sam should be able to turn the estimate in the week of 6/13-6/17. *SJH 6/10/22

## 6.2.22
Team Meeting
2022-06-02
Present: Wes, Sam, CJ, Stephanie (the fab 4)
Topics
1.) | Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed) | [6 empty] | WESCO
2.) | Estimator meeting with oscar tomorrow morning.
3.) | Health Insurance Renewal | [6 empty] | MEDICAL BENEFITS
4.) | Clean up active job list
5.) | Added Wesco as vendor on all HRP properties | [7 empty] | BCBS | BCBS | BCBS | BCBS | BCBS | UHC
6.) | Add church st to active jobs list (Isn't it there? Line 19) in sharepoint | [7 empty] | Current | Renewal | Gold 2000 | Silver 3500 | Silver 4500 | 7000 HSA
7.) | PO# Inventory 6146 (last 4 of phone #); Vendors are getting bad about not putting PO# on invoices | [6 empty] | Deductible | 7000 | 7000 | 2000 | 3500 | 4500 | 7000
PROJECTS | [7 empty] | Total Out Of Pocket | 7000 | 7000 | 6000 | 8700 | 8700 | 7000
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date | Primary Office Visit | Ded., 0% | Ded., 0% | $25 copay | $50 copay | $50 copay | Ded., 0%
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Building 1& 2 exteriors are mostly finished. We will have material he needs to finish except green 4x10 by end of day 6-2. | Needs (30) pcs Green (Mountain Sage) 4x10 panel ASAP | 2022-07-31 | Specialist Office Visit | Ded., 0% | Ded., 0% | $50 copay | $100 copay | $100 copay | Ded., 0%
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Rogelio finishing roof on kayak 6-2 | waiting on colors for dumpster gates | 2022-04-30 | Outpatient Services | Ded., 0% | Ded., 0% | Ded., 20% | Ded., 30% | Ded., 30% | Ded., 0%
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | Where are we with punch list. We need to make our own punch list before Hawthorne. | Still waiting on last truck of shake and panel | 2022-06-30 | Inpatient Services | Ded., 0% | Ded., 0% | Ded., 20% | Ded., 30% | Ded., 30% | Ded., 0%
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May | Need 5/4 trim for bands. All shingles are onsite. Follow up about metal roofing. Wes royaly fucked up with scheduling that made his life stressful. | Get shakes to job that are at Wes' house |  | Emergency Room | Ded., 0% | Ded., 0% | $600 copay | $1000 copay | $1000 copay | Ded., 0%
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Frame chases on first floor for plumbing/hvac. Drawing for center beam repair. | Need to get drawing to KMW for structural beam repair. CO sent to KMW for subfloor and beam repair that has already taken place. *SJH 5/20/22 |  | Prescription | Ded., 0% | Ded., 0% | $4/$15/$35/$50/25% | $15/$40/$80/$120/25% | $15/$40/$80/$120/25% | Ded., 0%
KMW Leo Loso/Gateway @ CLT Park | Wes | Rogelio 4/13 | Cipriano June-August |  | Lansing is bringing in 30 piece of 4x10 for someone to pick colors off of once they are installed on the garage. | Install siding on garages for color selections |  | Lifetime Maximum | Unlimited | Unlimited | Unlimited | Unlimited | Unlimited | Unlimited
KMW Retreat | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | CJ delivering 5/4x10 and 5/4x8 for door and window trim. Need to figure change order for columns and 5/4x8 trim next to doors/windows on patios. Follow up with lansing about 14" x12' soffit |  | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Job currently scheduled to begin in July '22, though Kyle McDowell says it could be as late as September '22. *SJH 5/27/22
St. Marks | SJH |  |  |  | Manuel will complete soffit and fascia on Friday, 5/27/22. Can not complete siding installation until brick is installed in 6-8 weeks. *SJH 5/27/22
Terrell St. | SJH |  |  |  | Finished | None | 4/25/22 - Complete
Windridge | Wes | Manuel | Manuel |  | Finished | None
Edgewater Village (4/22/22) | SJH |  |  |  | First unit was punched and completed on Tuesday, 5/17/22. Invoice has already been sent to Trey Melton and has been passed up to his corporate office for payment. *SJH 5/20/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | TKG to begin renovation installs (cabinets, door slabs, baseboard) week of 6/6-6/10/22. Marble Granite world to create template for hard-surface counters upon completion of millwork installs. Paint and flooring to be completed while counters are being manufactured. *SJH 6/2/22.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
Waterway |  |  |  |  | We need to verify pricing. Contract showed up in my email 6-2-22
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | TKG to begin renovation installs (cabinets, door slabs, baseboard) week of 6/6-6/10/22. Marble Granite world to create template for hard-surface counters upon completion of millwork installs. Paint and flooring to be completed while counters are being manufactured. *SJH 6/2/22.
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Waterway |  |  |  |  | Bid Submitted on 5/12/22. *SJH 5/27/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 5/27/22
KMW - Maynard Rd. |  |  |  |  | Bid due on 6/21/22 *SJH 6/2/22

## 5.26.22
Team Meeting
2022-05-27
Present: Wes, Wes, CJ, Stephanie (the fab 4)
Topics
1.) | Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel (Bolded if prepared; green if executed)
2.) | ESTIMATOR!!!
3.) | Quickbooks 2022
4.) | Health Insurance Renewal
5.)
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Building 1& 2 are mostly complete, with some porches and a handful of faces being the only items remaining to be completed on those two. Building 3 has not yet been started. Cipriano was on vacation during my visit. SJH removed (1) pallet of Hardie soffit and brought it back to the office. *SJH 5/27/22 | Cipriano needs a pallet of trim coil to be delivered in Haywood ASAP. *SJH 5/27/22 | 2022-07-31
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Yohan heading Monday May23 to finish garage and kyak roof |  | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | TC still waiting on colors for shake on clubhouse - none yet; boomlift incident on retaining wall (painters); Abel finishing punch lists 2, 1, 7 & clubhouse | Next builidng starting - material should arrive this week | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May | Superior to deliver bldg 1 materials on Tuesday, 5/31/22. Zavala to begin roofing installation on Thursday, 6/2/22. *SJH 5/27/22
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Rigo at Church Street installing plastic over window openings on first floor *SJH 5/20/22 | Need to get drawing to KMW for structural beam repair. CO sent to KMW for subfloor and beam repair that has already taken place. *SJH 5/20/22
KMW Leo Loso/Gateway @ CLT Park | Wes | Rogelio 4/13 | Cipriano June-August |  |  | We need colors from KMW & RFI for trim around the windows. Sam to review plans for flashing details.
KMW Retreat | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Siding installation began on week of 5/23-5/27. DWA to complete mock-column using EZ Trim and 5/4 board. Visit planned for next week to begin column instruction and installation. 120' Boom to be delivered on Tuesday, 5/31/22. *SJH 5/27/22 | Sam to review plans for flashing details. | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Job currently scheduled to begin in July '22, though Kyle McDowell says it could be as late as September '22. *SJH 5/27/22
St. Marks | SJH |  |  |  | Manuel will complete soffit and fascia on Friday, 5/27/22. Can not complete siding installation until brick is installed in 6-8 weeks. *SJH 5/27/22
Terrell St. | SJH |  |  |  | Payment was dropped off to Stephanie from Tara on Wednesday, 5/18/22. *SJH 5/20/22 | None | 4/25/22 - Complete
Windridge | Wes | Manuel | Manuel |  | Job is Complete | None
Edgewater Village (4/22/22) | SJH |  |  |  | First unit was punched and completed on Tuesday, 5/17/22. Invoice has already been sent to Trey Melton and has been passed up to his corporate office for payment. *SJH 5/20/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | TKG to begin renovation installs (cabinets, door slabs, baseboard) week of 6/6-6/10/22. Marble Granite world to create template for hard-surface counters upon completion of millwork installs. Paint and flooring to be completed while counters are being manufactured. *SJH 6/2/22.
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | TKG to begin renovation installs (cabinets, door slabs, baseboard) week of 5/30-6/3/22. Marble Granite world to create template for hard-surface counters upon completion of millwork installs. Paint and flooring to be completed while counters are being manufactured. *SJH 5/27/22.
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22
HRP Waterway |  |  |  |  | Bid Submitted on 5/12/22. *SJH 5/27/22
HRP Brightwood Farms |  |  |  |  | Bid Submitted on 5/25/22. *SJH 2/27/22

## 5.19.22
Team Meeting
2022-05-19
Present: Wes, Wes, CJ, Stephanie (the fab 4)
Topics
1.) | Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel
2.) | Estimator
3.) | Quickbooks 2022
4.)
5.)
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  |  |  | 2022-07-31
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Yohan heading Monday May23 to finish garage and kyak roof |  | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | TC still waiting on colors for shake on clubhouse - none yet; boomlift incident on retaining wall (painters); Abel finishing punch lists 2, 1, 7 & clubhouse | Next builidng starting - material should arrive this week | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May | Start roofing on Tuesday June 1st Superior to deliver starting materials to office Friday May 27th | Get materials ordered with Larry @ Superior for delivery Monday *SJH - 6/1/22
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Rigo at Church Street installing plastic over window openings on first floor *SJH 5/20/22 | Need to get drawing to KMW for structural beam repair. CO sent to KMW for subfloor and beam repair that has already taken place. *SJH 5/20/22
KMW Leo Loso/Gateway @ CLT Park | Wes | Rogelio 4/13 | Cipriano June-August |  |  | We need colors from KMW & RFI for trim around the windows. Sam to review plans for flashing details.
KMW Retreat | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 | Beginning siding on Tuesday, 5/24/22. Sam to come down on Wednesday, 5/25/22. *SJH 5/20/22 | Sam to review plans for flashing details. | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | All preordered materials have arrived and are either on-site or in Wesco warehouse | Job currently scheduled to begin in July '22. *SJH 5/20/22
St. Marks | SJH |  |  |  | Manuel is installing soffit, fascia, and gable B&B on building 5. Poolhouse is 90% complete, but waiting on doors to be installed before completion is possible. *SJH 5/20/22 | Manuel will be there all of the following week (5/23-5/27). *SJH 5/20/22
Terrell St. | SJH |  |  |  | Payment was dropped off to Stephanie from Tara on Wednesday, 5/18/22. *SJH 5/20/22 | None | 4/25/22 - Complete
Windridge | Wes | Manuel | Manuel |  | Job is Complete | None
Edgewater Village (4/22/22) | SJH |  |  |  | First unit was punched and completed on Tuesday, 5/17/22. Invoice has already been sent to Trey Melton and has been passed up to his corporate office for payment. *SJH 5/20/22 | None
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | Majority of materials are in our warehouse. Waiting on appliances and cabinets (cabinets ready for pickup on 5/20/22). TKG to begin installs next week on 5/23 or 5/24, then paint & flooring, then final install. *SJH 5/20/22 | Get cabinets, door slabs, and baseboard to unit for install by Tuesday, 5/24/22. *SJH 5/20/22
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Punch List completed on 5/17/22 *SJH 5/20/22 | None
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | Majority of materials are in our warehouse. Waiting on appliances and cabinets (cabinets ready for pickup on 5/20/22). TKG to begin installs next week on 5/23 or 5/24, then paint & flooring, then final install. *SJH 5/20/22 | Follow up with vendors as finishes are selected to push contract forward. *SJH - 4/14*
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin
KMW - Wesleyan Homes | Not KW |  |  | Kyle McDowell | Initial pricing estimate sent to KMac on Thursday, 5/19/22. *SJH 5/20/22
HRP Murrayville |  |  |  |  | Potentially starting on first week of June - waiting on contract approval. *SJH 5/20/22

## 5.12.22
Team Meeting
2022-05-12
Present: Wes, Wes, CJ, Stephanie (the fab 4)
Topics
1.) | Subcontractor Contracts - Due 6/1/22 Haywood II Zavala/Cipriano/Manuel; Holly Springs - Abel; Retreat @ Carteret Abel; Charlotte Park - Villeda; Crest Villeda & Yohan; Pine Forest II Abel & Zavala; Hillstone; WindRidge - Manuel
2.) | Estimator
3.) | Upcomming Projects Starting
4.) | We all need to take better pictures while on jobs
5.) | $1m umbrella policy for subs
6.) | Next week - Wes out of office in meetings Tues/Wed;
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  |  | CJ to take green siding to HII | 2022-07-31
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Rigo picked up last bit of materials TODAY (5-12-22) | Rigo completing gutters, need to scheduled another truck for this week. | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | TC still waiting on colors for shake on clubhouse - none yet; boomlift incident on retaining wall (painters); Abel finishing punch lists 2, 1, 7 & clubhouse | Next builidng starting - material should arrive this week | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May | Start roofing on Monday May 16th 2022 | Get materials ordered with Larry @ Superior for delivery Monday *SJH - 5/12/22
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Doors ordered through GCL on Wednesday, 4/13/22. Delivery ETA has not yet been given. *SJH - 4/14* | Need to get drawing to KMW for structural beam repair. CO sent to KMW for subfloor and beam repair that has already taken place. *SJH 5/12/22
KMW Leo Loso/Gateway @ CLT Park | Wes | Rogelio 4/13 | Cipriano June-August |  | EZ trim delivered on Wednesday, 4/13/22 - organized and put into container by Roy. Josh is still to determine siding color for 1-coat painting. *SJH - 4/14* | We need colors from KMW & RFI for trim around the windows. Sam to review plans for flashing details.
KMW Retreat | Wes | Abel Gamboa | Through 6-30(Crew 2) | estimated 5/25/22 |  | Sam to review plans for flashing details. | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | All preordered materials have arrived and are either on-site or in Wesco warehouse
St. Marks | SJH |  |  |  | Waiting on Bldg 5 brick to be completed, as well as breezeway gyp-crete so that we can install siding. *SJH 5/12/22
Terrell St. | SJH |  |  |  | Job is Complete - Waiting on second payment
Windridge | Wes | Manuel | Manuel |  | Job is Complete
Edgewater Village (4/22/22) | SJH
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Small punch list to be completed by TKG
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | Met with Sterling on 4/14 to determine hard-surface counter finishes. Setting up meeting with GYF to choose tile backsplash finishe. Contract pricing will be updated and approved per Sterling Kelly. *SJH - 4/14* | Follow up with vendors as finishes are selected to push contract forward. *SJH - 4/14*
Partnership
PPM-Kings Crossing | Not KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | Not KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | Not KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | Not KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | Not KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | Not KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | Not KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | Not KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | Not KW |  |  | Jason Bufkin

## 4.28.22
Team Meeting
2022-04-28
Present: Wes, Kyle, Wes, CJ, Stephanie
Topics
1.)
2.)
3.)
4.)
5.)
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Site visits 4/13 & 4/14 - Started siding Wed 4/13, stair completion underway, shingles to be dlivered Monday morning (Bldg 2 under construction then 1) *4/14 DWA* | Roofing material delivery scheduled for Friday, 4/15/22. Zavala to begin install on Monday, 4/18/22. Metal roofing materials to be ready for pick-up @ TCM by CoB 4/14.*SJH - 4/14* | 2022-07-31
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Half material is out remaining scheduled 4/21; 1 boom gone, 1 picked up. Forklift picked up 4/13. *4/14 DWA* | Rigo completing gutters, need to scheduled another truck for this week. | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | TC still waiting on colors for shake on clubhouse - none yet; boomlift incident on retaining wall (painters); Abel finishing punch lists 2, 1, 7 & clubhouse | Next builidng starting - material should arrive this week | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May |  | SA to prepare pay apps for material billing.
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Doors ordered through GCL on Wednesday, 4/13/22. Delivery ETA has not yet been given. *SJH - 4/14*
KMW Leo Loso/Gateway @ CLT Park | Wes | Rogelio 4/13 | Cipriano June-August |  | EZ trim delivered on Wednesday, 4/13/22 - organized and put into container by Roy. Josh is still to determine siding color for 1-coat painting. *SJH - 4/14* | We need colors from KMW & RFI for trim around the windows. Sam to review plans for flashing details.
KMW Retreat | Wes |  | Abel through May (Crew 2) | estimated 5/25/22 | Sam to follow up with W. Palma regarding door installation. Need to check on nailing pattern for panel and siding - no significant details in Hardie's product page. *SJH - 4/14* | Sam to review plans for flashing details. | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | Storm doors were delivered into container on Tuesday, 4/12/22. Container locked. Email sent to Banner to check on door hardware - Material list and order was sent to them on 11/17/21 per email correspondance. *SJH - 4/14*
St. Marks | SJH | Manuel |  |  | Zavala is installing metal roofs on risers on Thursday, 4/14/22. Rogelio to complete siding on riser extensions on Friday, 4/15/22. *SJH - 4/14*
Terrell St. | SJH | Rigo |  |  | Waiting on arrival of new bathroom wall paneling - delivery scheduled for Monday, 4/18/22. Job will be complete once wall paneling, vanity, and toilet are installed in bathroom. *SJH - 4/14* | Need Rigo to install paneling and button up job on Tuesday, 4/19/22 *SJH - 4/14* | 2022-04-15
Windridge | Wes | Manuel | Manuel |  | Working on 2nd to last bldg - and wrapping up 1st bldg | Need to get 4x10 panels to Manuel next week. Will likely need (20)+ panels. *SJH - 4/14*
Edgewater Village (4/22/22) | SJH
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Property is awaiting the delivery of their material package. The bulk of the order should be on-site before 4/25. Doors will be installed first, then paint and flooring, then completion of material install. *SJH - 4/14* | Sam to meet with Trey on 4/18 or 4/19 to discuss final details before renovation begins. *SJH - 4/14*
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | Met with Sterling on 4/14 to determine hard-surface counter finishes. Setting up meeting with GYF to choose tile backsplash finishe. Contract pricing will be updated and approved per Sterling Kelly. *SJH - 4/14* | Follow up with vendors as finishes are selected to push contract forward. *SJH - 4/14*
Partnership
PPM-Kings Crossing | KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | KW |  |  | Jason Bufkin

## 4.21.22
Team Meeting
4/21/2022 (4/18)
Present: Wes, Kyle, Wes, CJ, Stephanie
Topics
1.) | This week - Wes Vac Wed-Fri; SA - Thurs & Fri; CJ - Thurs & Fri
2.) | Tues - CJ&Kyle - Holly Springs = punch list & inventory & rec'v shipment; Wed - CJ Doors; Thurs - Door Install Chadwick (Sam will schedule Rogelio for Thurs&Fri)
3.) | Equipment - Service Tracking - Ues of Equipment Form
4.)
5.)
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Site visits 4/13 & 4/14 - Started siding Wed 4/13, stair completion underway, shingles to be dlivered Monday morning (Bldg 2 under construction then 1) *4/14 DWA* | Roofing material delivery scheduled for Friday, 4/15/22. Zavala to begin install on Monday, 4/18/22. Metal roofing materials to be ready for pick-up @ TCM by CoB 4/14.*SJH - 4/14* | 2022-07-31
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Half material is out remaining scheduled 4/21; 1 boom gone, 1 picked up. Forklift picked up 4/13. *4/14 DWA* | Rigo completing gutters, need to scheduled another truck for this week. | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | TC still waiting on colors for shake on clubhouse - none yet; boomlift incident on retaining wall (painters); Abel finishing punch lists 2, 1, 7 & clubhouse | Next builidng starting - material should arrive this week | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May |  | SA to prepare pay apps for material billing.
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Doors ordered through GCL on Wednesday, 4/13/22. Delivery ETA has not yet been given. *SJH - 4/14*
KMW Leo Loso/Gateway @ CLT Park | Wes | Rogelio 4/13 | Cipriano June-August |  | EZ trim delivered on Wednesday, 4/13/22 - organized and put into container by Roy. Josh is still to determine siding color for 1-coat painting. *SJH - 4/14* | We need colors from KMW & RFI for trim around the windows. Sam to review plans for flashing details.
KMW Retreat | Wes |  | Abel through May (Crew 2) | estimated 5/25/22 | Sam to follow up with W. Palma regarding door installation. Need to check on nailing pattern for panel and siding - no significant details in Hardie's product page. *SJH - 4/14* | Sam to review plans for flashing details. | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | Storm doors were delivered into container on Tuesday, 4/12/22. Container locked. Email sent to Banner to check on door hardware - Material list and order was sent to them on 11/17/21 per email correspondance. *SJH - 4/14*
St. Marks | SJH | Manuel |  |  | Zavala is installing metal roofs on risers on Thursday, 4/14/22. Rogelio to complete siding on riser extensions on Friday, 4/15/22. *SJH - 4/14*
Terrell St. | SJH | Rigo |  |  | Waiting on arrival of new bathroom wall paneling - delivery scheduled for Monday, 4/18/22. Job will be complete once wall paneling, vanity, and toilet are installed in bathroom. *SJH - 4/14* | Need Rigo to install paneling and button up job on Tuesday, 4/19/22 *SJH - 4/14* | 2022-04-15
Windridge | Wes | Manuel | Manuel |  | Working on 2nd to last bldg - and wrapping up 1st bldg | Need to get 4x10 panels to Manuel next week. Will likely need (20)+ panels. *SJH - 4/14*
Edgewater Village (4/22/22) | SJH
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton | Property is awaiting the delivery of their material package. The bulk of the order should be on-site before 4/25. Doors will be installed first, then paint and flooring, then completion of material install. *SJH - 4/14* | Sam to meet with Trey on 4/18 or 4/19 to discuss final details before renovation begins. *SJH - 4/14*
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | Met with Sterling on 4/14 to determine hard-surface counter finishes. Setting up meeting with GYF to choose tile backsplash finishe. Contract pricing will be updated and approved per Sterling Kelly. *SJH - 4/14* | Follow up with vendors as finishes are selected to push contract forward. *SJH - 4/14*
Partnership
PPM-Kings Crossing | KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | KW |  |  | Jason Bufkin

## 4.14.22
Team Meeting
2022-04-14
Present: Wes, Kyle, Wes, CJ
Topics
1.) | Closed Friday, 4/15
2.) | Safety Recalls Duramax diesel 6.6 liter engine and optional engine block heater cord - HS 2018 Chevy Silverado; 2019 Chevy Silverado (Sam & Wes)
3.)
4.)
5.)
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II | Wes | Cipriano | Cipriano mid-April-June |  | Zavala to begin installing bldg 3 roof on Tuesday, 4/19/22. Metal roofing to be installed starting Wednesday, 4/20/22. Roofing mats delivered on Friday, 4/15/22. S&W taking metal roofing up on Tuesday, 4/19/22. *SJH 4/18" |  | 2022-07-31
HRP Crest (5/2021) | Wes |  | Rigo Mon-Thurs Future Hillstone & Cipriano Punch |  | Half material is out remaining scheduled 4/21; 1 boom gone, 1 picked up. Forklift picked up 4/13. *4/14 DWA* | Rigo completing gutters, need to scheduled another truck for this week. | 2022-04-30
HRP Holly Springs | Wes | Abel Gamboa | Abel through June (Crew 1) |  | TC still waiting on colors for shake on clubhouse - none yet; boomlift incident on retaining wall (painters); Abel finishing punch lists 2, 1, 7 & clubhouse | Next builidng starting - material should arrive this week | 2022-06-30
HRP Pine Forest II (4/16/22) | Wes |  | Abel through Sept (Crew 3) | estimated start mid-May
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Left message with Gerardo on 4/18/22. Will update as soon as labor is confirmed for this. *SJH - 4/18*
KMW Leo Loso/Gateway @ CLT Park | Wes | Rogelio 4/13 | Cipriano June-August |  | Josh is still to determine siding color for 1-coat painting. *SJH - 4/18* | We need colors from KMW & RFI for trim around the windows
KMW Retreat | Wes |  | Abel through May (Crew 2) | estimated 5/25/22 | Sam emailed Wayne on 4/18 to check on door installation approval. Need to check on nailing pattern for panel and siding - no significant details in Hardie's product page. *SJH - 4/18* |  | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | Hardware from Banner began to come in on Monday, 4/18/22. Remaining materials to be received by Friday, 4/22/22. *SJH - 4/18*
St. Marks | SJH | Manuel |  |  | Metal roofing and vinyl siding installed on riser rooms on Thursday & Friday, 4/14 & 4/15. *SJH - 4/18*
Terrell St. | SJH | Rigo |  |  | Waiting on arrival of new bathroom wall paneling - delivery postponed to Wednesday, 4/20/22. Job will be complete once wall paneling, vanity, and toilet are installed in bathroom. *SJH - 4/18* | Need Rigo to install paneling and button up job on Wednesday, 4/20/22 *SJH - 4/14* | 2022-04-15
Windridge | Wes | Manuel | Manuel |  | Working on 2nd to last bldg - and wrapping up 1st bldg. 4x10 panels available in Statesville, but SJH is still trying to find delivery for this week. S&W to see if there is enough white panel @ Haywood to supply Manuel until the replacement materials are available. *SJH - 4/18* | Need to get 4x10 panels to Manuel next week. Will likely need (20)+ panels. *SJH - 4/14*
Edgewater Village (4/22/22) | SJH |  |  |  | SJH talked to Trey on Monday, 4/18 - material package is not yet complete. Trey to update with ETA's on outstanding items ASAP so that schedule can be put in place.*SJH - 4/18*
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill |  |  |  |  | Updated pricing sent for this project
Wakefield (2/2023) |  |  |  |  | Hardie pricing verification and hold request sent to C. Little on 4/13. Will update if anything changes drastically. *SJH - 4/14*
Edgewater Village | SJH | TKG Renovations | ~4/25 | Trey Melton
Chadwick Place |  | Roy | 2022-04-21 |  | Rogelio to begin installing storm doors on (24) units. To begin on Thursday, 4/21/22. *SJH - 4/18*
Pipeline/Bids | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Courtyard Commons | SJH | TKG Renovations | TBD | Derek Evans | Met with GYF and D. Evans to discuss tile backsplash on Monday, 4/18. Final estimate to be sent for approval as soon as this pricing is received. *SJH - 4/18*
Partnership
PPM-Kings Crossing | KW |  |  | Jason Bufkin | Stair replacement, site steps, sidewalk plates
PPM - Plantation Village | KW |  |  | Jason Bufkin | Roofing, Windows, Dumpster Fence, Mailbox Posts, 8x8
PPM - Silver Trace Apts | KW |  |  | Jason Bufkin | Stair Tread replacement, mailbox posts (8x8)
PPM - Little Pee Dee Manor | KW |  |  | Jason Bufkin | Gazebo Enclosure, Fountain pricing
PPM - Churchwood Apts | KW |  |  | Jason Bufkin | 2 story bay window replacement , accent siding, aluminum columns per PM
PPM - Greenfield | KW |  |  | Jason Bufkin | Storage room doors, roof replacement, siding pricing per building
Mountain Glen | KW |  | 2022-08-22 | KMW | Submitted, revising pricing per Kevin
KMW - Hartwood Village | KW |  |  |  | Roofing, windows, interior doors, hardware, dumpster fence | Waiting on pricing back on interior doors/windows from GCL, ABC
PPM - Westridge Apts. | KW |  |  | Jason Bufkin

## 4.8.22
Team Meeting
2022-04-08
Present: Wes, Kyle, Wes, CJ, Stephanie
Topics
1.) | Closed Friday, 4/15
2.) | Using daily job sheets
3.) | Take notes when at the jobs
4.) | Lets get bids out quickly while they are fresh on our minds
5.) | Move jobs from in process to completed
6.)
7.)
PROJECTS
Current Projects (Start Date) | Project Manager | Subcontractor & Schedule THIS WEEK | Subcontractor & Schedule NEXT WEEK/FUTURE | Upcoming Job Site Visit Date | Weekly Job Summary (Materials Ordered/Arrival Date/Work Performed/Action Taken) | Action Items Next Week (Change Order Submission Needed/Unsafe Conditions/Materials/Opportuities) | Estimated Job Completion Date
HRP Haywood II |  | Cipriano | Cipriano mid-April-June
HRP Crest (5/2021) |  |  |  |  | Moving materials out ASAP and Boom Lift. Have forklift Picked up on last day of cycle |  | 2022-04-30
HRP Holly Springs |  | Abel Gamboa | Abel through June (Crew 1) |  | TC still waiting on colors for shake on clubhouse |  | 2022-06-30
HRP Pine Forest II (4/16/22) |  | Abel Gamboa | Abel through Sept (Crew 3)
KMW Church St Lofts (4/2022) | SJH |  | Gerardo? |  | Order Trim and doors next week. Get schedule for framing and drywall - need to find solution for storing doors on-site since framing will be handled in multiple phases.
KMW Leo Loso/Gateway @ CLT Park |  |  | Cipriano June-August |  | EZ Trim to be delivered week of 4/11/22, J. Blevins to determine color of siding for 1-coat painting.
KMW Retreat |  | Abel Gamboa | Abel through May (Crew 2) |  |  |  | 2022-05-30
KMW Springfield | SJH |  | Pato? |  | Storm Doors to be delivered on 4/12/22. Labor finders setup to be there @ 9am. Get schedule
St. Marks | SJH | Manuel |  |  | Riser room extensions to get vinyl siding and metal roof - (1) on bldg 3 and (1) on bldg 4. Caleb to approve C/O.
Terrell St. | SJH | Rigo |  |  |  |  | 2022-04-15
Windridge
Edgewater Village (4/22/22)
Upcoming Projects (Start Date) | Project Manager | Subcontractor |  |  | Weekly Planning Summary (Materials Ordered/Arrival Date/Change Order Submission Needed/Unsafe Conditions/Opportuities) | Action Items This Week | Estimated Start Date
HRP Mill
Wakefield (2/2023)
Pipeline | Project Manager | Anticipated Subcontractor | Estimated Start Date | Customer Contact | Bid Status | Action Needed/Comments | Estimated Start Date
Edgewater Village
HRP - Mill